{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Table 1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Table 1","index":0,"n_rows":295,"n_cols":19,"rows_kept":295,"cut":false,"hidden":false,"merged":[[131,13,131,14],[132,13,132,14],[182,0,183,0],[229,0,230,0],[182,1,183,1],[229,1,230,1],[182,2,183,2],[229,2,230,2],[182,3,183,3],[229,3,230,3],[182,4,183,4],[229,4,230,4],[182,5,183,5],[229,5,230,5],[182,6,183,6],[229,6,230,6],[182,7,183,7],[229,7,230,7],[182,8,183,8],[229,8,230,8],[182,9,183,9],[229,9,230,9],[182,10,183,10],[229,10,230,10],[182,11,183,11],[229,11,230,11],[182,12,183,12],[229,12,230,12],[182,13,183,13],[229,13,230,13],[182,14,183,14],[229,14,230,14],[182,15,183,15],[229,15,230,15],[182,16,183,16],[229,16,230,16],[182,17,183,17],[229,17,230,17],[182,18,183,18],[229,18,230,18]]}
["Street","FULL ADDRE SS","ZIPC ODE","PROJECT NAME","DESCRIPTION","PLANNE R","SRC","CDD","ZA","DRC","PC","CC","FINAL APPR OVAL DATE","NOTES","Submi ttal Date","STATU S UPDA TED (DATE ONLY)","APPLICAN T NAME","APPLICANT EMAIL","APPLIC ANT PHONE"]
["Adams","837 E\nAdams Ave","9286\n7","Heidi Chen Chew","Conversion of an existing RV garage into a two bedroom\nADU","Tiffany Chhan",null,"Pendi ng",{"$nulls":5},"Comment letter sent 8/18/21","7/20/2\n021","8/18/2\n021","Heidi Chew",null,"(949)\n233-\n8868"]
["Adams","1502 E\nAdams Ave","9286\n7","Navarret e Multi- Family ADU","Multi-Family garage conversion into a 663 square foot\nADU.","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"8/22/2\n022",null,null,"9/27/2\n022","Oscar Vega","oscar.vega@vecodesign s.com","(714)\n499-\n1297"]
["Adams","1929 E\nAdams\nAve","9286\n7","Adams Ave ADU","Construct a detached\n1,000 SF ADU","Monique Schwartz",null,"Pendi ng",{"$nulls":5},"Incomplet e Letter","12/15/\n2022","2/10/2\n023","Abraham Shakolas","abrahamshakolas@gma il.com","(714)\n458-\n8650"]
[{"$nulls":4},"on a multifamily\nproperty.",{"$nulls":8},"sent 2/6/2023"]
["Acacia","1040\nW.\nAcacia Ave","9286\n8","Capello Garage Conversio n ADU","Garage conversion to a one bedroom ADU","Monique Schwartz",null,"Pendi ng",{"$nulls":5},"Latest Incomplet e letter sent 9/6/2022","5/17/2\n022",null,"Jordon Capello","jordan@capelloplumbin g.com","(626)\n622-\n1773"]
["Agate","2089 N\nAgate\nSt","9286\n7","Ramirez Residenc\ne","A request to add two bedrooms and three bathrooms to an existing single family residence, and construct a detached ADU\nand garage.","Monique Schwartz",null,"Pendi ng",{"$nulls":5},"Comment Letter sent 3/16/202\n1",null,"9/28/2\n022","Antonio Ramirez","newportdraftservice@g mail.com","(714)\n650-\n9588"]
["Americ an","2390 N\nAmeric an Way","9286\n5","Industrial Bldgs.","Demolition of existing on-site development and construction of two industrial\nbuildings.","Monique Schwartz","Appr oved",null,null,"Approved","Approve d",null,"10/17/\n2022","Building Plans in plan check",null,"1/18/2\n023","Brandon Wolfe","bwolfe@epdsolutions.c om","(949)\n872-\n4838"]
["Arlingto n","553 S\nArlingto n Rd","9286\n9","Millard Addition and ADU","New second story addition and convert existing living space on first floor into an ADU.","Ryan Agbayani",{"$nulls":7},"11/28/22\n- Second incomplet e letter emailed to applicant.","10/12/\n2022",null,"Sondra Millard","sondramillard@gmail.c om","(714)\n803-\n8319"]
["Avenid a Palmar","5227 E\nAvenid a Palmar","9286\n9","Ha Residenc e","A request to construct an\naddition to an existing single-","Monique Schwartz",null,"Appro ved",{"$nulls":4},"4/29/2\n020","Planning final inspection",null,"9/28/2\n022","Angelina Ha","angelinaha@gmail.com","(949)\n370-\n6624"]
[{"$nulls":4},"family residence.",{"$nulls":8},"complete d"]
["Avenid a\nPalmar","5218 E\nAvenid a\nPalmar","9286\n9","Ngam Ha ADU","A new 800 square foot detached ADU with 2 bedrooms and\n2 bathrooms","Monique Schwartz",null,"Appro ved",{"$nulls":5},"CDD\napproval on 8-16-\n22",null,"1/18/2\n023","Vinh Pham","vinhpham58@yahoo.co m","(714)\n390-\n6841"]
["Barkley","413 E\nBarkley\nAve","9286\n7","Stout ADU","Construct a new detached\n633 SF ADU.","Emily Golubow",null,"Pendi ng",{"$nulls":5},"Sent initial comment letter to applicant on\n3/15/23.","2/15/2\n023",null,"Roy Riveroy Jr","rriveroy@yahoo.com","(626)\n827-\n1772"]
["Barkley","2818 E\nBarkley Ave","9286\n7","Gutierrez ADU","A new 406 square foot attached\nstudio ADU","Tiffany Chhan",null,"Appro ved",{"$nulls":4},"9/27/2\n022",null,"4/22/2\n022","9/27/2\n022","Jose L Gutierrez","joe1454@yahoo.com","(714)\n615-\n1320"]
["Batavia","456 N\nBatavia St","9286\n8","Jiang ADU","Construction of a new detached 800 square foot ADU and a 485 square foot addition to the existing single- family dwelling.\nDemolition of an existing 216 square foot storage building.","Ray Pascua (Contract Planner)",null,"Appro ved",{"$nulls":5},"CDD\napproval on 1/24/23","8/16/2\n022","11/27/\n2022","Mark Murphy","mark@stack-llc.com","(310)\n803-\n6510"]
["Batavia","2060 N\nBatavia St","9286\n8","FXI\nWarehou se","New warehouse building to replace fire\ndamage buildings.","Vidal F. Márquez","Pendi ng","Pendi ng",{"$nulls":6},"12/22/\n2022",null,"Mie McVicker","mmcvicker@fxi.com","(608)\n697-\n3231"]
["Batavia","2425 N\nBatavia St","9286\n8","DISH\nWireless","Dish Wireless wanting to mount on existing mono- eucalyptus tower consisting of two (2) panel\nantenna and 2 RRUs per sector mounted on 43' centerline and camouflaged with necessary ancillary radio equipment at grade in the existing CMU enclosure. FCC 6409(a)\ncandidate.","Vidal F. Márquez",{"$nulls":8},"11/3/2\n022",null,"Brian De La Ree","bdlaree@core.us.com","(323)\n273-\n2199"]
["Berkele y","2557 N\nBerkele y St","9286\n5","Lamphea r ADU","New detached 550 SF ADU\n(one bedroom, one bathroom) at rear of\nproperty","Ryan Agbayani",null,"Pendi ng",{"$nulls":5},"3/13/23 -\nIncomplet e Letter emailed to\napplicant.","1/31/2\n023","3/13/2\n023","Brian Lamphear","blamphear@hotmail.co m","(714)\n345-\n3215"]
["Beverly","2343 W\nBeverly Dr","9286\n8","Dang Detached ADU","New 1,000 SF\ndetached ADU consisting of two bedrooms and two baths","Monique Schwartz",null,"Appro ved",{"$nulls":5},"Pending receipt of Deed Restrictio n Building plans under\nreview","9/19/2\n022","1/18/2\n023","Kathy Mai Dang","dangkathy@yahoo.com","(714)\n622-\n0785"]
["Bitterb ush","266 N\nBitterb ush St","9286\n8","Maldinin Detached\nADU","Convert existing 512 SF\ndetached","Monique Schwartz",null,"Pendi ng",{"$nulls":5},"Incomplet e Letter","1/5/20\n23","2/10/2\n023","Micky Maldini","ktrenddesign@gmail.co m","(657)\n347-\n8219"]
[{"$nulls":4},"garage into an ADU",{"$nulls":8},"sent 2/8/2023"]
["Bobwhi te","122\nBobwhi te Way","9286\n9","Melkonia n ADU","Convert existing 3 car garage to a 549 SF ADU.","Ray Pascua (Contract Planner)",null,"Appro ved",{"$nulls":5},"CDD\napproval on 1/17/202\n3","10/25/\n2022","11/27/\n2022","Raffi Melkonian","raffi.melkonian@att.ne t","(714)\n308-\n3394"]
["Bradbu ry","3126 E\nBradbu ry Ct","9286\n7","Sheikh Residenc e","Construction of a new 11,728 square foot single- family residence on a\nvacant lot.","Tiffany Chhan",null,"Pendi ng",{"$nulls":5},"Comment letter sent 6/7/22","5/23/2\n022","6/7/20\n22","Masroor Sheikh","sheikh.masroor7@gmai l.com","(562)\n392-\n0312"]
["Burley","2737\nBurley Ave","9286\n9","Herzog ADU","Convert and existing garage to an ADU","Monique Schwartz",null,"Appro ved",{"$nulls":4},"8/30/2\n022",null,null,"11/1/2\n022","Anat Herzog","aagozliving@gmail.com","(949)\n933-\n0604"]
["Cabrillo","1326 N\nCabrillo St","9286\n9","Aggarwal Addition","Proposed two- story addition to a single story residence with attached garage.","Ryan Agbayani",null,"Correc tions",{"$nulls":5},"2/8/23 -\nApplicant resubmitt ed revised plans.",null,"10/20/\n2022","Sanjiv Kumar Aggarwal","littleindia@outlook.co m","(657)\n456-\n2867"]
["Cambri dge","252 N\nCambri dge St","9286\n6","Bogart Addition\nand ADU","Addition and remodel for an\nADU","Ani Mnatsak\nanyan",null,"Pendi ng",null,"Pending",null,null,null,"Continued to 4/5/23","10/5/2\n022","2/10/2\n023","Kevin Bogart","kevin@wgbib.com","(714)\n401-\n7676"]
["Cambri dge","291 N\nCambri dge St","9286\n6","291 N\nCambridg e ADU","A proposal to convert an existing 432 SF detached garage into an\nADU","Historic Preservat ion",null,"Appro ved",{"$nulls":7},"8/10/2\n022","Luis Lopez","design@oc- builders.com"]
["Cambri dge","339 N\nCambri dge St","9286\n6","339 N\nCambridg e ADU","New proposed 864 SF\ndetached ADU","Ani\nMnatsak anyan",null,"Appro ved",{"$nulls":4},"2/28/2\n023",null,"12/13/\n2022",null,"Edward Osuch","eddie@neo-inc.com","(626)\n590-\n1818"]
["Cambri dge","560 N\nCambri dge St","9286\n7","Refael ADU","New detached 799 SF ADU","Monique Schwartz",null,"Pendi ng",{"$nulls":6},"3/8/20\n23",null,"Fady Tawadrou\ns","f_tawadrous@hotmail. com","(760)\n885-\n5951"]
["Cambri dge","956 N\nCambri\ndge St","9286\n7","Fady Tawadro\nus","Conversion of an existing garage into a\n390 SF ADU","Tiffany Chhan",null,"Pendi ng",{"$nulls":5},"Comment letter sent\n8/13/21","8/3/20\n21","8/13/2\n021","Fady Tawadrou\ns","f_tawadrous@hotmail. com","(760)\n885-\n5951"]
["Cambri dge","1550 N\nCambri dge St","9286\n7","Dish Wireless","New wireless facility to be mounted on\nan SCE tower","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"3/17/2\n022","Approved",null,"4/6/20\n22"]
["Cambri dge","1550 N\nCambri dge St","9286\n7","AT&T\nCambridg e","AT&T wireless facility collocation on an existing SCE Tower.\nEquipment to be located in a chain link enclosure below the\ntower.","Ray Pascua (Contract Planner)","Pendi ng","Pendi ng",{"$nulls":5},"Approval pending on Fire Departme nt Review and\nApproval","6/27/2\n022","11/27/\n2022","Jermaine Taylor","jttelecoms@gmail.com","(909)\n917-\n1727"]
["Cambri dge","426 S\nCambri dge St","9286\n6","Maloney Residenc e","A proposal for a 280 SF\naddition and 200 SF\ncovered patio.","Ani Mnatsak anyan",null,null,null,"Approved",null,null,null,"DRC Date: 12/7/22",null,"9/21/2\n022","Jonathan Ma","jonm@designxarchitect s.com","(949)\n463-\n4521"]
["Cannon","1502\nCannon St","9286\n7","AT&T\nWireless","AT&T Wireless Facility","Vidal F. Márquez",{"$nulls":10},"Jermaine Taylor","jttelecoms@gmail.com","(909)\n917-\n1727"]
["Carver","5925 E\nCarver\nLn","9286\n7","DISH\nWireless","Dish wireless requesting a colocation on an existing non-stealth wireless\nfacility.","Ryan Agbayani",null,"Pendi ng",{"$nulls":6},"2/15/2\n023",null,"Sylvia Duran","sduran@tepgroup.net","(619)\n980-\n5422"]
["Century","1415 &\n1417 E\nCentury\nDr","9286\n6","Home Expo Group Develop ment Addition and Remodeli\nng","Two-story addition of 3,549 SF living\narea and 461 SF attached garage and refacing existing 685 SF\nADU.","Vidal F. Márquez",null,"Pendi ng",{"$nulls":6},"3/6/20\n23",null,"Steven Letran","steven@slpdesigninc.co m","(714)\n388-\n8996"]
["Century","1415 E\nCentury\nDr","9286\n6","Home Expo Group Develop ment New\nJADU","New proposed 495 SF JADU","Vidal F. Márquez",null,"Pendi ng",{"$nulls":6},"3/6/20\n23",null,"Steven Letran","steven@slpdesigninc.co m","(714)\n388-\n8996"]
["Chandl er Ranch","490 N\nChandl er Ranch Rd","9286\n9","Khaja Retaining Wall","Proposed 8 foot retaining wall.","Emily Golubow",null,null,"App. not need ed",{"$nulls":4},"AA not needed. File Closed.","12/2/2\n022",null,"A Khaja","alikhaja@hotmail.com","(805)\n952-\n3517"]
["Chapm an","208 E\nChapm an Ave","9286\n6","Centro Orange","Tenant improvement for an Italian eatery and cafe, including a new patio cover for outdoor seating at the\nrear.","Ani Mnatsak anyan",null,null,null,"Pending",{"$nulls":4},"2/7/20\n23",null,"Enrico Pozzvoli","enrico@pozzoliwinery.c om","(714)\n915-\n7450"]
["Chapm an","208 E\nChapm\nan Ave","9286\n6","Centro Orange","Request for an ABC Type ??\nLicense at an Italian Restaurant\nand Cafe.","Ani Mnatsak\nanyan",{"$nulls":4},"Pending",null,null,null,"2/9/20\n23",null,"Enrico Pozzvoli","enrico@pozzoliwinery.c om","(714)\n915-\n7450"]
["Chapm an","407 E\nChapm an Ave","9286\n6","Dish Wireless","Proposed Dish Wireless facility","Ani Mnatsak anyan",null,null,null,"Pending",{"$nulls":4},"12/8/2\n022",null,"Brian De La Ree","bdelaree@core.us.com","(323)\n273-\n2199"]
["Chapm an","1610 E\nChapm\nan Ave","9286\n6","Core Burger","Exterior and interior remodel of an existing commercial building into a restaurant with outdoor\nseating","Monique Schwartz","Appr oved","Appro ved",{"$nulls":4},"3/21/2\n022",null,null,"1/18/2\n023","Pako Pimsagua\nn","ppinsaquan@kineticdes ign.build","(951)\n710-\n6334"]
["Chapm an","1610 E\nChapm an Ave","9286\n6","Core Burger","ABC Type 41 Request for new\nRestaurant","Vidal F. Márquez",{"$nulls":4},"Pending",null,null,"Scheduled for 9/8 PC meeting",null,"9/1/20\n22","Phil Bacerra","phil@philbacerra.com"]
["Chapm an","2503 E\nChapm an Ave","9286\n9","Chapman Yorba VIII","Proposed general plan amendment and zone change to allow for the development of 158 senior apartments and storage\nfacility.","Robert Garcia","Pendi ng",null,null,"Pending","Pending","Pendi ng",null,"Address is for reference only. The project site is south of the Santa Ana River at the intersecti on of Chapman Ave and Yorba St. SRC\nReview 07-20-22",null,"2/22/2\n023","Robert C. Pack Stonefield Developm ent","bobpack@stonefieldde velopment.com","(949)\n581-\n4663"]
["Chapm an","2503 E\nChapm an Ave","9286\n9","SB 330\nChapman Yorba","Preliminary Review for a proposal to construct 204 apartment units including 41 affordable units within two six-story\napartment","Robert Garcia","Com plete",{"$nulls":6},"Address is for reference only. The project site is south of the Santa Ana River\nat the","1/24/2\n023","3/10/2\n023","Robert C. Pack Stonefield Developm\nent","bobpack@stonefieldde velopment.com","(949)\n933-\n9590"]
[{"$nulls":4},"buildings totaling 227,932 SF\nand a 113,590 SF three-story self-storage building with 298 parking spaces on a\nvacant site.",{"$nulls":8},"intersecti on of Chapman Ave and Yorba St."]
["Chapm an","2940 E\nChapm an Ave","9286\n9","NEXX\nBurger","A proposal to demolish an existing restaurant and construct a new fast food drive-through\nrestaurant.","Monique Schwartz","Appr oved",null,null,"Approved","Approve d","Appr oved","7/13/2\n021",null,null,"9/28/2\n022","Darian Radac","darian@novumarchitec ture.com","(310)\n709-\n4476"]
["Chapm an","3208 E\nChapm an Ave","9286\n9","Friendly Animal Hospital","A proposal to construct a new 3,125 square foot veternary hospital on unimproved\nland.","Ryan Agbayani","Pendi ng",null,null,"Pending","Pending",null,null,"2/16/23 - SRC\ncomment letter emailed to\napplicant","12/6/2\n022","1/24/2\n023","Marcus Kemmerer","marcus@kdarch.com","(71)\n465-\n3139"]
["Chapm an","4530 E\nChapm an Ave","9286\n9","El Portal De Veracruz Restaura nt","A request for a Type 41 Beer and Wine ABC license for the El Portal De Veracruz Restaurant.","Ryan Agbayani",{"$nulls":4},"Approve d",null,"2/23/2\n023","2/23/23 -\nPlanning Commissi on approved the CUP (see Reso No. PC\n04-23).","6/14/2\n022","10/31/\n2022","Ankit Patel","inkarainc@gmail.com","(714)\n686-\n8914"]
["Chapm an","240 W\nChapm an Ave","9286\n6","Snooze Outdoor Dining","Proposal for new outdoor dining layout\nalong S. Lemon Street","Historic Preservat ion",null,"Pendi ng",{"$nulls":5},"Comment s Letter sent 4/28/202\n2",null,"8/30/2\n022","240 West Chapman Partners LLC",null,"(714)\n330-\n2941"]
["Chapm an","401 W\nChapm an Ave","9286\n6","Old Towne Gateway","A proposal to rehabilitate two historic buildings for restaurant uses in the Old Towne Historic District, demolish non- historic sheds, and construct two new one- story commercial\nbuildings.","Anna Pehoush ek","Appr oved",null,null,"Recomme ndation of Denial to Planning Commissi on on 9/8/22","Recomm ended approval to City Council on 10/17/2\n2","Appr oved","11/15/\n2022","DRC\nrecomme nded Denial to Planning Commissi on 9/8/22;\nscheduled for 10/17/22 PC\nmeeting",null,"11/28/\n2022","Leason Pomeroy III, LP3\nArchitectu re,","lp3arch@aol.com","(714)\n771-\n8400"]
["Chapm an","730 W\nChapm an Ave","9286\n6","Clark Station","Construction of 3,642 SF\nmulti-tenant retail building with site improvements\n.","Ani Mnatsak anyan",null,null,null,"Pending",{"$nulls":4},"11/14/\n2022",null,"Leason Pomeroy III, LP3\nArchitectu re,","lp3arch@aol.com","(714)\n771-\n8400"]
["Chapm an","814 W\nChapm an Ave","9286\n8","Chapman\n+ Clark","A proposal to remodel a non- contributing building into four office/retail\nsuites","Historic Preservat ion","Pendi ng",null,null,"Pending",null,null,null,"On hold",null,"3/28/2\n022","Myrna J Livingston Trust",null,"(714)\n536-\n8764"]
["Chapm an","2620 W\nChapm\nan Ave","9286\n8","7-Eleven Gas\nStation","Demolish an existing drive- through restaurant and construct a new 4,319- square foot convenience store with fuel\nservice and","Vidal F. Márquez","Appr oved",null,null,"Approved","Approve d",null,"11/1/2\n020","Permits issued",null,"11/18/\n2021","Joe Buonya",null,"(626)\n328-\n6752"]
[{"$nulls":4},"associated site improvements"]
["Chapm an","2620 W\nChapm an Ave","9286\n8","7-Eleven Gas Station","Request for new ABC License type 20 Off-Sale\nBeer and Wine","Vidal F. Márquez",{"$nulls":4},"Pending",null,null,"Routed for PD review",null,"1/17/2\n021","Adan Madrid","adan@7pcd.com","(714)\n519-\n3399"]
["City","500\nWest City\nPkwy","9286\n8","T-Mobile Rooftop Wireless\nFacility","Construct a wireless communicatio n facility on office building screened by FRP walls on 3 building\ncorners.","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"2/25/2\n021"]
["Clark","365 N\nClark St","9286\n8","Kearl ADU","New attached 745 SF ADU in\nthe front setback and garage converison to a 231 SF a\nJADU.","Ani Mnatsak anyan",null,"Pendi ng",{"$nulls":6},"1/13/2\n023","2/10/2\n023","Brian Scott","brian@plansbybrian.co m","(888)\n271-\n7526"]
["Clark","320 S\nClark St","9286\n8","Clark & Palmyra\nADU's","Conversion of three existing detach garages\ninto ADU’s","Ani Mnatsak\nanyan",null,"Appro ved",{"$nulls":8},"Rolando Serrano","serranoarch11@gmail.c om","(323)\n508-\n6127"]
["Cliffway","6123 E\nCliffway Dr","9286\n9","Morada Residenc e","A request to construct an addition, and outdoor recreation/ent ertainment facilities to an existing\nresidence.","Monique Schwartz",null,"Pendi ng",{"$nulls":5},"Comment letter sent 6/30/202\n1",null,null,"Lane Curtis","lane.curtis@gmail.com","(714)\n381-\n8393"]
["Coate","654 S\nCoate Rd","9286\n9","Dickelma n Addition","A 573 SF\naddition to an existing second floor of a single family residence","Ryan Agbayani",null,"Pendi ng",{"$nulls":5},"3/2/23 -\nIncomplet e Letter emailed to applicant.","1/4/20\n23","3/2/20\n23","Kellen Carel","kellen@cstudio.pro","(714)\n254-\n5308"]
["Collins","300 E\nCollins Ave","9286\n7","SFR Lot Split; Gregory Roberts 300\nCollins LLC","Subdivision on an existing parcel into 2","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"10/20/\n2022","Final Map review by Public Works","1/10/2\n022","1/30/2\n023","D.\nWoolley & Associates\n, David woolley","dwoolley@dwoolley.co m","(714)\n734-\n8462"]
["Collins","500 W\nCollins\nAve","9286\n7","Orange Collins Logistics\nCenter","Demolition of the existing site for a new 128,953\nsquare foot concrete tilt- up warehouse facility and associated site improvements\n.","Ryan Agbayani","Pendi ng",{"$nulls":6},"3/1/23 - AB 52\nTribal Consultati on Request Letters sent out to appropria\nte groups.","11/10/\n2022",null,"Brookfield Properties\n, Adam\nSchmid","adam.schmid@brookfie ldproperties.com","(310)\n765-\n3265"]
["Collins","623 W\nCollins Ave","9286\n7","Dish Wireless","Proposed Dish Wireless facility","Ryan Agbayani","Appr oved","Appro ved",{"$nulls":5},"3/16/23 - CDD\nDetermin ation Letter emailed\nto applicant.",null,null,"Sylvia Duran","sduran@tepgroup.net","(619)\n980-\n5422"]
["Court","4215 E\nCourt\nAve","9286\n9","Garcia Second Duplex\nUnit","Construction of a new 1,240 square foot detached single-family residence as a second unit on a duplex- zoned\nproperty.","Emily Golubow","Pendi ng","Pendi ng",{"$nulls":6},"5/23/2\n022","5/23/2\n022","Alicia Pateyro\nGarcia","pateyrover7@gmail.co m","(714)\n538-\n9254"]
["Crater Lake","6014 E\nCrater Lake\nAve","9286\n7","Miller- Sublett Residenc\ne","A proposal to demolish the majority of an existing single- family residence and construct a\nnew home.","Monique Schwartz",null,"Appro ved",{"$nulls":4},"4/13/2\n020",null,null,"9/28/2\n022","John Herman",null,"(325)\n465-\n7066"]
["Denise","2626 E\nDenise Ave","9286\n7","Nguyen Residenc e","Demo existing residence and construct a new two story single family\nresidence.","Ryan Agbayani",null,"Pendi ng",{"$nulls":5},"12/5/22\nRA - Third incomplet e letter emailed to\napplicant.","11/23/\n2020","11/3/2\n022","Peter Hung","hungdhung@yahoo.co m"]
["Dunas","476 S\nDunas St","9286\n9","Nguyen ADU","A request to construct a new 438 square foot detached 1\nbedroom, 1\nbathroom ADU","Monique Schwartz",null,"Appro ved",{"$nulls":4},"1/10/2\n023",null,"11/21/\n2022","11/30/\n2022","David Nguyen","httn3g@gmail.com","(510)\n650-\n5699"]
["Earlha m","211 S\nEarlha m St","9286\n9",null,"Fire damage reconstruction and remodel","Vidal F. Márquez",null,"Pendi ng",{"$nulls":5},"Notices mailed 3/2/23 for CDD\nDetermin\nation","10/13/\n2022","3/8/20\n23","Joe Pagano","joe@paganocc.com","(949)\n836-\n1921"]
["Earlha m","221 S\nEarlha m St","9286\n9","Earlham Duplex","A request to construct two new detatched units and an attached ADU to the rear unit.","Ray Pascua (Contract Planner)","Pendi ng",null,null,"Pending",null,null,null,"2/8/2023\n-\nApplicant submitted responses to 1st set of comment s and revised plan.  Will be schedulin g for 2nd SRC\nmeeting.","8/24/2\n022","11/27/\n2022","Farshad Shagoshta shi","F-24158@gmail.com","(949)\n202-\n8903"]
["Eckhoff","759 N\nEckhoff St","9286\n8","IDI\nOrange","A proposal to remove all existing buildings and site improvements to construct two new warehouse buildings (Building 1 –\n189,380 and\nBuilding 2 –\n101,520) with ancillary office space on a 12.69-acre site.","Robert Garcia","Appr oved",null,null,"Approved","Pending",null,null,"SRC\nRecomme nded Approval on 01/23/20\n23 DRC\nRecomme nded Approval on 02/15/20\n23",null,"3/10/2\n023","Nicole Morse","nmorse@tbplanning.co m","(714)\n505-\n6360"]
["Elizabet h","506 E\nElizabet h Dr","9286\n7","Nguyen ADU and JADU","Proposal to convert a garage to a an ADU and construct a\nnew 1,000","Monique Schwartz",null,"Appro ved",{"$nulls":5},"Approved by CDD on 1/11/202\n3","8/15/2\n022","1/18/2\n023","Khang Joseph Nguyen","josephnguyen12682@g mail.com","(714)\n623-\n3597"]
[{"$nulls":4},"square foot detached ADU."]
["Emeral d","478 N\nEmeral\nd Dr","9286\n8","Salazar Residenc\ne","Construct a new second story addition to an existing single story SFR with an\nattached ADU.","Tiffany Chhan",null,"Pendi ng",{"$nulls":5},"Comment Letter sent\n4/8/22","1/28/2\n021","4/8/20\n22","Eric Luna","innovativEidea.el@gma il.com","(310)\n429-\n6386"]
["Esplana de","162 N\nEsplana de St","9286\n9","Sitea ADU","Garage conversion, plus addition, for an ADU on a multi-family\nproperty.","Ray Pascua (Contract\nPlanner)",null,"Pendi ng",{"$nulls":5},"Applicant placed the garage conversio n to an ADU on\nhold.","6/30/2\n022","11/27/\n2022","Fady Taluadrou s","fady.taluadrous1@gmai l.com","(760)\n885-\n5951"]
["Esplana de","162 N\nEsplana de St","9286\n9","Sitea Garage Addition","Proposed addition to existing attached garage for storage","Ray Pascua (Contract Planner)",null,"Appro ved",{"$nulls":5},"1/30/202\n3 - Plans reviewed and approved and returned to\nYolanda.",null,null,"Josh Sitea","jsitea@gmail.com","(949)\n278-\n2828"]
["Euclid","3819 E\nEuclid Ave","9286\n9","DeLeon ADU","New attached 675 SF ADU","Ray Pascua (Contract\nPlanner)",null,"Pendi ng",{"$nulls":5},"Comment letter sent 11/08/22","10/12/\n2022","11/27/\n2022","Abel DeLeon","abeldeleon1958@gmail com","(714)\n244-\n8340"]
["Everett","240 E\nEverett Pl","9286\n7","Dorsey Residenc e ADU","New detached 744 SF ADU\naddition","Tiffany Chhan",null,"Pendi ng",{"$nulls":5},"Comment Letter Sent 12-6-\n21","11/18/\n2021","12/1/2\n021","Daniel Burns","allinoneconst@sbcglob al.net","(714)\n283-\n8640"]
["Fairhav en","2201\nFairhav\nen Ave","9286\n9","Grace Church","A proposal to construct an enclosed 8,663 sq. ft., two-\nstory, pre-","Monique Schwartz","Appr oved",null,null,"Approved",null,null,"4/6/20\n22",null,null,"9/28/2\n022","Ken Agharokh","kaanda@aol.com","(949)\n463-\n3396"]
[{"$nulls":4},"manufactured steel sports building and related site improvements\n."]
["Fairmo nt","782 S\nFairmo nt Way","9286\n9","Massuco ADU","Conversion of an existing 360 SF workshop\ninto an ADU","Ryan Agbayani",null,"Pendi ng",{"$nulls":6},"3/16/2\n023",null,"Rafael Salas","salas1042001@msn.co m","(562)\n818-\n2003"]
["Fairway","937 E\nFairway Dr","9286\n6","Huliska ADU","Convert an existing 469 square foot garage to an\nADU.","Ray Pascua (Contract\nPlanner)",null,"Appro ved",{"$nulls":5},"CDD\napproval on 1/12/202\n3","8/1/20\n22","11/27/\n2022","Merkavah Studio, Judith\nCukier","judith@merkavahstudi o.com","(818)\n914-\n9474"]
["Fellows","611 E\nFellows Dr","9286\n5","Elizabeth Gilleland","Addition of a second story to a single family residence and conversion of a sunroom to\nliving area","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"11/1/2\n021",null,null,"11/18/\n2021"]
["Ferndal e","814 E\nFerndal e Ave","9286\n5","Copenhav er Addition","Addition of 164 SF to an existing single family\nresidence.","Ani Mnatsak anyan",null,null,null,"Pending",{"$nulls":4},"2/27/2\n023",null,"Kyle Digiantoni o","kdigi12@gmail.com","(714)\n632-\n9420"]
["Flower","295 S\nFlower\nSt","9286\n8","Living Stone Methodis\nt Church","Proposed façade\nchanges","Vidal F. Márquez",null,null,null,"Pending",{"$nulls":4},"3/10/2\n023",null,"Myung Chung","cmcarcheng@gmail.co m","(818)\n468-\n2505"]
["Flower","295 S\nFlower St","9286\n8","Living Stone Methodis t Church","Change of use from professional office to church with\nclasses","Vidal F. Márquez",{"$nulls":4},"Approve d",null,"11/15/\n2021","PC\nApproved","6/17/2\n021","3/8/20\n23","CMC\nMyung Chung","cmcarcheng@gmail.co m","(818)\n468-\n2505"]
["Flower","300 S\nFlower St","9286\n8","DISH\nWireless","New wireless communicatio n facility co- location on existing non- stralth mono-\npole.","Vidal F. Márquez","Appr oved",null,null,"Approved",null,null,"12/21/\n2022","DRC\nApproved","10/27/\n2022","3/8/20\n23","Taylor Bond","tbond@motiveis.com","(714)\n686-\n0712"]
["Frampt on","293 N\nFrampt on St","9286\n8","Cortes ADU","New attached 683 SF ADU\nand removal of an open patio and deck.","Monique Schwartz",null,"Pendi ng",{"$nulls":6},"3/8/20\n23",null,"Phally Chea","pchea814@gmail.com","(714)\n544-\n1242"]
["Frank","6411 E\nFrank Ln","9286\n9","Adapt design services","New construction of a 7500 SF preschool as part of the Salem Lutheran\nCampus.","Robert Garcia","Appr oved","Pendi ng",null,"Pending",null,null,null,"SRC\nApproved 11/16/20\n22",null,"2/22/2\n023","Anthony Dagestino","anthony@adaptdesigns ervices.com","(714)\n540-\n4700"]
["Garden Grove","3707 W\nGarden Grove Blvd","9286\n8","Everfence Corporati on","Request for fencing along the entire perimeter of the property with three\naccess gates","Vidal F. Márquez","Appr oved",null,"Appr oved",null,null,null,"8/10/2\n022","ZA\napproved 8/10/202\n2","7/27/2\n021","3/8/20\n23","Matthew Couper","mattc@everfence.com","(562)\n946-\n2872"]
["Garden Grove","3707 W\nGarden Grove\nBlvd","9286\n8","Everfence Corporati\non","Request for fencing along the entire perimeter of the property with three access gates. Exceed fence height in front\nyard.","Vidal F. Márquez","Appr oved",null,"Appr oved",null,null,null,"8/10/2\n022","ZA\napproved 8/10/202\n2","2/2/20\n22","4/14/2\n022"]
["Glassell","870 N\nGlassell St","9286\n7","Medical Office Building","Preliminary review for a proposed two","Monique Schwartz","Pendi ng",{"$nulls":8},"9/28/2\n022","Annie Tran",null,"(714)\n478-\n8665"]
[{"$nulls":4},"story medical office building"]
["Glassell","870 N\nGlassell St","9286\n7","Carrera Triplex","Preliminary application to demolish an existing 1,027\nsquare foot 1 story landscape supplies building and construct a new 2 story, 3 attached dwelling unit multiple- family structure totaling 2,724 square feet. A General Plan Amendment and Zone Change would be required for a formal\napplication.","Monique Schwartz","Pendi ng",{"$nulls":8},"7/13/2\n022","Raul Carrera","RR_Hauling@yahoo.co m","(714)\n737-\n1892"]
["Glassell","2829 N\nGlassell St","9286\n5","Discovery\n, LLC","Parking lot/exterior building\nmodifications","Monique Schwartz","Appr oved","Appro ved",{"$nulls":4},"4/20/2\n020",null,null,"9/28/2\n022","John Doan","discoverydayprogram@ hushmail.com","(714)\n892-\n0754"]
["Glassell","1095 N\nGlassell St","9286\n7","Orange Wine Inc.","ABC Type 21 upgrade to general alcohol for existing convenience\nstore","Vidal F. Márquez",{"$nulls":4},"Denied",null,"8/22/2\n022","PC denied 8/22/202\n2","1/15/2\n021","3/8/20\n23","Kevin Hufford","kevin@abcliquorco nsultants.com","(213)\n600-\n7355"]
["Glassell","1190 N\nGlassell St","9286\n7","Orange Liquor and More","New ABC Type 21 general alcohol for proposed convenience\nstore","Vidal F. Márquez",{"$nulls":4},"Pending",null,null,"PD\nRecomme ndation received; under review","6/18/2\n021","3/8/20\n23","Farhan Aljiryes","fredjca@aol.com"]
["Glassell","119 S\nGlassell St","9286\n6","Euro Cafe Orange Type 41","New ABC Type 41 alcohol permit for\nEuro Cafe","Ani Mnatsak anyan",{"$nulls":4},"Pending",null,null,null,"12/6/2\n022","12/6/2\n022","Euro Cafe Orange Circle Inc.","gstaella@yahoo.com","(714)\n222-\n4567"]
["Glassell","195 S\nGlassell St","9286\n6","Zinc Cafe/Frui t\nExchange","A request to serve alcohol in assocation with a new\nrestaurant.","Robert Garcia",{"$nulls":4},"Approve d",null,null,"PC\napproved on 11/7/202\n2","5/31/2\n022","12/22/\n2022","Fruit Exchange at 195 Todd\nCottle","todd@c-cdev.com","(714)\n288-\n7600"]
["Glassell","391 S\nGlassell St","9286\n6","McClean Design Variance","A request for a Variance to remove an existing ADA parking space at the rear of the building and gate parking area\nclosed.","Historic Preservat ion",{"$nulls":4},"Approve d",null,"5/2/20\n22","Reso 07-\n22\nscheduled for final approval on 5/16/22",null,"5/9/20\n22","Nathan Hunt","nathan@mccleandesign\n.com","(714)\n505-\n0556"]
["Glen Albyn","5230\nGlen Albyn Ln","9286\n9","Dish Wireless","Install of additional antennas and associated equipment to an existing wireless communicatio\nn facility.","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"3/25/2\n022","Approved",null,"4/6/20\n22","Kari Brown, Tower Engineeri ng","ktbrown@tepgroup.net","(952)\n292-\n9337"]
["Grand","231 N\nGrand St","9286\n6","Smith Residenc e ADU","Addition of 140 square feet to an existing 660 square foot garage for the\ncreation of an","Alvin Nuval (Contract Planner)",null,"Pendi ng",{"$nulls":7},"6/6/20\n22","Carl Shields","carl@oldtowneplumbin g.com","(714)\n532-\n6274"]
[{"$nulls":4},"800 square foot accessory dwelling unit."]
["Grand","850 N\nGrand St","9286\n7","Bianchi ADU","Construction of a new detached 749 square foot\nADU","Monique Schwartz",null,"Appro ved",{"$nulls":5},"Approved",null,"1/18/2\n023","Dustin Bianchi","greatwhitevinyl@gmail. com","(714)\n742-\n3535"]
["Grand","870 N\nGrand St","9286\n7","Grand Street ADU","New detached 800 square\nfoot, 2\nbedroom 2 bathroom ADU","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"8/23/2\n022","Approved","7/18/2\n022","8/23/2\n022","Jean Paul De Guzman","architect03@pionadg.c om","(714)\n400-\n2664"]
["Grand","257 N\nGrand St","9286\n6","Hartman Residenc e Garage","Demolition of an existing 2 car garage and workshop and construction of a new 2 car garage, workshop, and habitable bonus room in the ½ story\nabove.","Ani Mnatsak anyan",null,null,null,"Continued to 4/5/23",null,null,null,"DRC Date 12/21/22;\ncontinued to 4/5/23 DRC","8/1/20\n22","8/1/20\n22","Rick Fox, Stratos Form","rfox@stratosform.com","(714)\n628-\n0777"]
["Grand","337 S\nGrand St","9286\n6","Leaming ADU","Request to permit an existing ADU that was created without a building\npermit.","Alvin Nuval (Contract Planner)",null,"Pendi ng",{"$nulls":6},"6/20/2\n022","6/21/2\n022","Kim Leaming","kleaming5@gmail.com","(562)\n787-\n6069"]
["Grand","413 S\nGrand St","9286\n6","Murray Residenc e","Single story addition to the rear of an\nexisting house.","Ani Mnatsak anyan",null,null,null,"Pending",{"$nulls":4},"12/20/\n2022",null,"Daniel Murray","danjpmurray@gmail.co m","(805)\n205-\n4709"]
["Grand","424 S\nGrand St","9286\n6","Drenner Garage","A reqeust to construct a new detached","Ani Mnatsak anyan",null,null,"Pendi ng","Approved on 3/1/23",null,null,null,"DRC Date: 12/21/22; DRC","8/25/2\n022","8/31/2\n022","Tom Aldrich, DSEA Inc.","taldrich@dseainc.com","(714)\n639-\n3958"]
[{"$nulls":4},"garage and modify a rear wood fence.",{"$nulls":8},"continued to 3/1/23"]
["Grand","529 S\nGrand\nSt","9286\n6","Vukovich Duplex\nUnit","Construct a new 1,525 square foot detached\nduplex unit.","Anna Pehoush\nek",null,null,null,"Approved on\n10/5/22","Appeal of DRC Approva l Denied on\n12/5/22","Appe al  of PC\nActio n 2/14/\n23","2/14/2\n022","CC denied appeal of\nPC action.","5/19/2\n022","2/14/2\n023","Michael & Alison\nVukovich","mikevukovich@gmail.c om","(949)\n295-\n6755"]
["Grand","515 S\nGrand St","9286\n6","515 S.\nGrand Street Duplex\nUnit","Consutrct a new second dwelling unit on a contributing property in the Old Towne Historic\nDistrict.","Anna Pehoush ek",null,null,null,"Denied on 10/19/22",{"$nulls":5},"11/2/2\n022","Tom Aldrich, DSEA Inc.","taldrich@dseainc.com","(714)\n639-\n3958"]
["Greenvi ew","1331 E\nGreenvi ew Dr","9286\n6","Salazar ADU","Conversion of an existing covered patio to a 495 square foot accessory\ndwelling unit.","Ray Pascua (Contract Planner)",null,"Appro ved",{"$nulls":4},"8/31/2\n022","CDD\napproval on 2/1/2023","6/8/20\n22","11/27/\n2022","Marlyn Salazar","venus1201@yahoo.co m","(909)\n904-\n3052"]
["Grove","301 E\nGrove Ave","9286\n5","Phillip Schwartz e","A proposal to redevelop an existing shopping center with 32 detached condominiums and related\non-site\nimprovements","Monique Schwartz","Appr oved",null,null,"Approved","Approve d","Appr oved","12/8/2\n020",null,null,"9/28/2\n022","Phil Schwartze","phillipschwartze@gmail\n.com","(949)\n300-\n8619"]
["Grove","632 E\nGrove Ave","9286\n5","Grove ADU","Proposed addition of 112 SF and\nnew attached 746 SF ADU at","Monique Schwartz",null,"Pendi ng",{"$nulls":6},"3/14/2\n023",null,"Sam Olson","sampacificlegacy@gmai l.com","(909)\n702-\n5860"]
[{"$nulls":4},"rear of existing residence"]
["Grovew ood","7417 E\nGrovew ood Ln","9286\n9","Wahi Residenc e","A proposal to remodel and add onto an existing single family residence and construct a new detached\ngarage","Monique Schwartz","Appr oved",null,"Appr oved",null,null,null,"10/13/\n2021",null,null,"9/28/2\n022","Peggy Hsu","peggy@hm.la","(310)\n463-\n9573"]
["Hamilto n","2900 E\nHamilto n Ave","9286\n7","Carlos Guerrero","New 382 sq. ft. attached ADU","Tiffany Chhan",null,"Pendi ng",{"$nulls":7},"1/18/2\n022","Carlos Guerrero","ggiancalo@yahoo.com","(714)\n482-\n1262"]
["Hamlin","506 N\nHamlin St","9286\n9","Vasquez Residenc e","New 2nd story addtion","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"1/20/2\n022","Ready to issue permit","6/15/2\n022","2/28/2\n022","Richard Stauffer","rcad26@aol.com"]
["Hamlin","506 N\nHamlin St","9286\n9","Garo ADU","Partial conversion of an attached 450 SF garage into a 372 SF\nADU","Emily Golubow",null,"Pendi ng",{"$nulls":6},"1/24/2\n023",null,"Lily Garo","lgaro2020@gmail.com","(714)\n600-\n8961"]
["Handy","459 N\nHandy St","9286\n7","Jablonski ADU","vm","Ray Pascua (Contract\nPlanner)",null,"Appro ved",{"$nulls":4},"9/23/2\n022","Plans in Plan Check; Need Deed Restrictio\nn","6/9/20\n22","11/27/\n2022","Robert Quintero","robertquin.rq@gmail.c om","(909)\n567-\n5670"]
["Hariton","660 N\nHariton St","9286\n8","Hariton Industrial","Addition to an industrial building consisting of 9,481 SF of\nwarehouse.","Vidal F. Márquez","Pendi ng",null,null,"Pending",null,null,null,"Comment letter sent 2/10/23","10/13/\n2022","3/8/20\n23","Ken Hultgren","kenthehulk@yahoo.co m","(714)\n803-\n8443"]
["Hartma n","3196 N\nHartma n St","9286\n5","Crabtree ADU","New detached 320 SF ADU.","Ray Pascua (Contract\nPlanner)",null,"Pendi ng",{"$nulls":5},"Comment letter sent 11/08/22","10/13/\n2022","11/27/\n2022","Bashar A","bashar@sdsstructural.c om","(949)\n292-\n3340"]
["Heathe rstone","872 S\nHeathe rstone St","9286\n9","Keschrum rus Garage","Garage expansion where the garage door exceeds eight\nfeet in height","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"9/9/20\n22",null,"1/18/2\n022","9/29/2\n022","Vin Keschrum rus","keschrumrus@yahoo.c om"]
["Hewes","140 N\nHewes St","9286\n9","Hewes Duplex","Request to construct a duplex on existing vacant\nproperty","Vidal F. Márquez","Pendi ng",null,null,"Pending",null,null,null,"Comment letter sent 2/24/23","3/8/20\n22","3/8/20\n23","Bao Pham","bpdo.connect@gmail.c om"]
["Hewes","491 N\nHewes St","9286\n9","St. Verena Coptic Orthodox\nChurch","Construct 13,000 sq. ft. sports and spiritual\ncenter.","Vidal F. Márquez","Appr oved",null,null,"Pending","Pending",null,null,"DRC\nContinued Item to April 19,\n2023","10/6/2\n021","3/8/20\n23","James Thayer","main@tmlsarc.com"]
["Hewes","555 S\nHewes St","9286\n9","AT&T\nMobility","Proposal for a non-stealth wireless\nfacility","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"10/21/\n2022","CDD\napproval on 10/21/20\n22","4/7/20\n22","3/8/20\n23","Jermaine Taylor"]
["Highlan d","660 N\nHighlan\nd St","9286\n7","Page ADU","Convert an exisitng 400 SF attached garage into an\nADU","Emily Golubow",null,"Pendi ng",{"$nulls":5},"Sent comment letter to applicant on\n01/11/23","12/12/\n2022",null,"Sean Page","seanepage@gmail.com","(707)\n331-\n0322"]
["Highlan d","777 N\nHighlan d St","9286\n7","Siegried Wheelcha ir Lift","A request to relocate a wheelchair lift in the interior clear space of a garage.\nThe proposal is associated with a residential addition for a new","Vidal F. Márquez",null,"Pendi ng",{"$nulls":5},"Under review","11/22/\n2022","2/15/2\n023","James Siegried","jamessiegfried44@gmai l.com","(619)\n252-\n9933"]
[{"$nulls":4},"bathroom and hallway interconnect ion of an isolated bedroom to the interior of the existing dwelling. A patio cover and spa is also component of the overall work."]
["Heim","1815 E\nHeim Ave","9286\n5","Dish Wireless","Proposed Dish Wireless facility","Ryan Agbayani","Pendi ng","Pendi ng",{"$nulls":5},"3/1/23 -\nProject presented to SRC, who provided comment\ns. SRC Comment Letter emailed to\napplicant.",null,null,"Sylvia Duran","sduran@tepgroup.net","(619)\n980-\n5422"]
["Katella","1325 W\nKatella Ave","9286\n7","Rapids Express Car Wash (Katella)","A proposal to demolish the existing restaurant and to construct a new express car wash building with vacuum areas. The car was building is\ncomposed of","Anna Pehoush ek","Appr oved",null,null,"Approved","Approve d","CC\nheari ng on 11/1\n5/22",null,"PC\nrecomme nded approval to CC, CC\nscheduled for 11/15/22.",null,"11/2/2\n022","Geoff Von Der Ahe","geoff@rapidsexpress.co m","(949)\n235-\n4382"]
[{"$nulls":4},"three areas: 1) an east tower control office with a mezzanine, 2) a car wash tunnel and equipment room, and 3) a west tower for storage and equipment.\nVacuum area will have fabric canopies with vacuum hoses"]
["Katella","1623 W\nKatella Ave","9286\n7","Pittfire Pizza ABC","ABC Type 47 permit for full on and off-site consumption in conjunction with a restaurant and Design Review for façade modifications including an expanded outdoor dining area and\nsignage.","Vidal F. Márquez",{"$nulls":4},"Approve d",null,null,"PC\nApproved","5/23/2\n022","2/15/2\n023","Jeffrey Goodman","jeff@agfcorp.com","310.77\n3.5069"]
["Katella","1936 E\nKatella Ave","9286\n7","Dental Office and Training Facility","A proposal to demolish an existing restaurant and construct a new 9,884 sq. ft. two story dental office\nand training facility, and","Monique Schwartz","Appr oved",null,null,"Approved","Approve d",null,"11/6/2\n021",null,null,"11/15/\n2022","Bruno Boval","alanboval@hotmail.co m","562-\n552-\n1344"]
[{"$nulls":4},"related on site improvements\n."]
["Katella","1938 E\nKatella Ave","9286\n7","American Tower","A proposal to remove and replace an existing CMU wall and wireless facility\nequipment.","Monique Schwartz",{"$nulls":9},"11/15/\n2022","American Tower",null,"949-\n788-\n8900"]
["Katella","901 E\nKatella\nAve","9286\n7","Intracorp Homes","Proposal to change the General Plan Land Use Element designation from General Commercial to Medium Density Residential 15-\n24 du/ac and Zoning from Commercial Professional to Residential Multiple Family. 52 paired and detached homes are proposed on the site with a tentative tract\nmap.","Ray Pascua (Contract\nPlanner)","Pendi ng",null,null,"Pending","Pending","Pendi ng",null,"Comment letter sent\n10/23/22","8/16/2\n022","11/27/\n2022","Intracorp Homes - Emilie\nSimard","esimard@intracorphom es.com","(949)\n724-\n5923"]
["Katella","114 E\nKatella Ave","9286\n7","AO\nArchitect s","Addition of a new drive-thru window to an","Vidal F. Márquez","Appr oved","Appro ved",null,null,"Approve d",null,"3/21/2\n022","PC\nApproved 3/21/202\n2","8/13/2\n021","3/9/20\n23","AO\nArchitects"]
[{"$nulls":4},"existing restaurant"]
["Katella","720 E\nKatella Ave","9286\n7","Juan Del Rio Mendoza","ABC Type 47 Request for existing\nrestaurant","Vidal F. Márquez",{"$nulls":4},"Approve d",null,"9/7/20\n22","PC\napproved on 9/7/2022","3/23/2\n022","3/8/20\n23","Ivan Lozada","ivan@liquorlicenseagen ts.com"]
["Katella","830 E\nKatella Ave","9286\n7","Mobil Gas Station Remodel","409 sq. f. addition to existing convenience store and\nremodel.","Vidal F. Márquez","Appr oved",null,null,"Approved",null,null,"8/19/2\n022","Under contructio n","11/5/2\n018","3/9/20\n23","Jose Pozzobon","jpozzobon@msn.com"]
["Katella","830 E\nKatella\nAve","9286\n7","Mobil Gas Station\nRemodel","ABC Type 20 Request for existing service station\nstore","Vidal F. Márquez",{"$nulls":4},"Pending",null,null,"Under Police Dept\nReview","11/5/2\n018","3/9/20\n23","Jason Kno","jason@aaaliquorlicense s.com"]
["Katella","1611 E\nKatella\nAve","9286\n7","El Pollo Loco Facade\nRemodel","Exterior modifications to an El Pollo Loco including horizontal panels and\ncanopies","Ray Pascua (Contract\nPlanner)",null,"Appro ved",{"$nulls":5},"CDD\napproval on 12/7/202\n2","7/28/2\n022","11/27/\n2022","Patrick Faranal","pfaranal@namc.com","(909)\n287-\n7375"]
["Kenny mead","1277 N\nKenny mead Rd","9286\n9","Elder Accessory Structutu re","Proposed detached 1,400 SF pre-\nfab accessory structure; new one-car garage (273 SF), new\nroom addition (209 SF), and\nsecond room addition (121 SF)","Ryan Agbayani",null,"Pendi ng",{"$nulls":5},"3/9/23 -\nMinor correction s and clarificati ons emailed to\napplicant.","12/13/\n2022","3/9/20\n23","Joe Lambert","joe@cp-services.biz","(714)\n812-\n9157"]
["Kenny mead","1441 N\nKenny mead Rd","9286\n9","Danny Duong","new 1950 SF 4-car garage, tennis court, and sports\ncourt","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":7},"4/14/2\n022"]
["Killings worth","2727 E\nKillings worth Ave","9286\n9","Agreda ADU","New detached 750 SF ADU","Ryan Agbayani",null,"Appro ved",{"$nulls":5},"1/19/23 - CDD\nApproval Letter sent to applicant. Project is approved.","10/6/2\n022","10/20/\n2022","Romulo Agreda","lito.arrowgeneralcontra ctors@gmail.com","(714)\n366-\n4968"]
["La Veta","437 E\nLa Veta Ave","9286\n6","Carr Garage Rebuild","A request to rebuild a garage on an Old Towne property due\nto disrepair and age","Alvin Nuval (Contract Planner)",null,null,null,"Pending",{"$nulls":4},"7/12/2\n022","7/20/2\n022","Brenda Carr","brendacarr4realty@yah oo.com","(714)\n404-\n0595"]
["La Veta","1800 E\nLa Veta Ave","9286\n6","IUSA\nPropertie s","Redevelopmen t of the existing Rio Rehabilitation Center site with a new 166 unit affordable senior apartment\nproject.","Monique Schwartz","Appr oved",null,null,"Approved","Approve d",null,"3/7/20\n22",null,null,"10/12/\n2022","Leatha Clark","lclark@usapropfund.co m","(91)\n686-\n5391"]
["La Veta","3752 E\nLa Veta Ave","9286\n9","NMurriet ta SFD Infill","Preliminary review of a proposal to subdivide an abandoned railroad ROW and construct 5 new single family\nresidences.","Ryan Agbayani","Pendi ng",{"$nulls":6},"Address is for reference only. The project site is the abandone d Southern Pacific Railroad ROW\nlocated south of La Veta and north of Fairhaven\n, and west of Chipwood and east of Woodlan\nd.","2/28/2\n023",null,"David Maldonad o","dmalsonado@D33Desig n.com","(949)\n230-\n4537"]
["La Veta","617 W\nLa Veta Ave","9286\n8","HomeAid ADU","HomeAid ADU project to provide shelter for families and seniors in need. City of Orange owns\nproperty","Ani Mnatsak anyan",null,null,"Pendi ng",{"$nulls":5},"11/2/2\n022",null,"Yvette Ahlstrom","yvette@homeaidoc.org","(949)\n301-\n9896"]
["La Veta","625 W\nLa Veta Ave","9286\n8","HomeAid ADU","HomeAid ADU project to provide shelter for families and seniors in\nneed. City of","Ani Mnatsak anyan",null,null,"Pendi ng",{"$nulls":5},"11/2/2\n022",null,"Yvette Ahlstrom","yvette@homeaidoc.org","(949)\n301-\n9896"]
[{"$nulls":4},"Orange owns property"]
["La Veta","637 W\nLa Veta Ave","9286\n8","HomeAid ADU","HomeAid ADU project to provide shelter for families and seniors in need. City of Orange owns\nproperty","Ani Mnatsak anyan",null,null,"Pendi ng",{"$nulls":5},"11/2/2\n022",null,"Yvette Ahlstrom","yvette@homeaidoc.org","(949)\n301-\n9896"]
["La Veta","920 W\nLa Veta\nAve","9286\n8","Orange Healthcar e and Wellness\nCenter","Request for a 6 foot high fence in front\nsetback","Vidal F. Márquez","Appr oved",null,"Appr oved",null,null,null,"8/10/2\n022","ZA\napproval on\n8/10/22",null,"9/28/2\n022"]
["La Veta","1142 W\nLa Veta Ave","9286\n8","St. Joseph Parking Structure Space Reductio n","Parking Structure Repair for St. Joseph Medical Plaza. The AA allows for a reduction in parking stalls to accommodate safety implementatio\nn measures.","Monique Schwartz",null,null,"Appr oved",{"$nulls":4},"ZA\napproval on 8/31/202\n2",null,"10/12/\n2022","Mark Valenzuel a","mvalenzuela@hbapm.c om","(310)\n436-\n3270"]
["Lakesid e","2344 E\nLakesid\ne Ave","9286\n7","Lakeside ADU","A reqeust to construct a new detached ADU (660 SF)\nat rear of property (1\nbedroom 1\nbathroom)","Tiffany Chhan",null,"Appro ved",{"$nulls":4},"8/26/2\n022","11/2/22 -\nApplicant must provided Grant Deed, which must be recorded\nprior to",null,"8/26/2\n022","Alder James / Armando\nCorrado","armando@alderjames.c om","(949)\n529-\n9012"]
[{"$nulls":13},"permit issuance."]
["Lemon","121 N\nLemon\nSt","9286\n6","Taco Adobe","Tenant improvement and expansion to a fire damaged\nrestaurant","Ani Mnatsak\nanyan",null,null,null,"Approved",null,null,null,"DRC Date 11/16/20\n22","10/24/\n2022","11/9/2\n022","Jeff Rabbitt","jeff@aoarchitects.com","(714)\n639-\n9860"]
["Lincoln","804 E\nLincoln\nAve","9286\n5","Olive Heights Sign Program Modificat\nion","A proposal to update the existing Master Sign Program for a commercial\ncenter.","Tiffany Chhan",null,"Pendi ng",{"$nulls":5},"Project on hold by\napplicant.",null,"12/15/\n2021","Mr. Patel","rashmi@aabhargroup.c om","(310)\n344-\n4352"]
["Lincoln","1440 E\nLincoln Ave","9286\n5","Del Taco Remodel, Lincoln Avenue","Proposed Del Taco exterior façade remodel involving roof form changes, a tower element, and revised exterior\nfinishes.","Vidal F. Márquez","Pendi ng",null,null,"Pending",null,null,null,"Comment letter provided 6/23/202\n2",null,"9/28/2\n022","Steve Shaw","steve@adnarch.com","(310)\n773-\n7772"]
["Lincoln","1606 E\nLincoln Ave","9286\n5","Nohl Plaza LLC","Proposed drive-through and new outdoor patio for a proposed\nrestaurant.","Vidal F. Márquez","Appr oved",null,null,"Approved","Approve d",null,"6/6/20\n22","PC\nApproved 6/6/2022","10/18/\n2021","2/23/2\n023","Greg James","gjames@mckently.com","(714)\n335-\n9104"]
["Lincoln","374 N\nLincoln\nSt","9286\n7","Walsh ADU","Proposal to construct a new 904 SF detached ADU (2 bedrooms 1 bathroom) at rear of\nproperty","Ryan Agbayani",null,"Appro ved",{"$nulls":4},"3/9/20\n23","3/9/23 - CDD\nApproval Letter emailed to\napplicant.",null,null,"Lam Nguyen","cumulusdesignbuild@g mail.com","(714)\n657-\n9333"]
["Lincoln","701 N\nLincoln St","9286\n7","Jiwani ADU","Proposal to convert a garage to an ADU.","Monique Schwartz",null,"Pendi ng",{"$nulls":5},"Incomplet e letter sent 11/23/20\n22","8/23/2\n022","1/18/2\n023","Abraham Lee","abraham.lee@nakomar ealty.com","(714)\n514-\n1766"]
["Linda Vista","1291 N\nLinda Vista St","9286\n9","Thorne Master Bath\nAddition","New master bath addition","Ani Mnatsak anyan",null,null,null,"Pending",null,null,null,"Comment letter sent 10/31/22","10/4/2\n022","11/9/2\n022","John & Julia Thorne","jpthorne61@gmail.com","(714)\n469-\n9069"]
["Locust","220 E\nLocust Ave","9286\n7","220314\nADU","A request to convert a garage to a 502 square\nfoot ADU.","Ray Pascua (Contract Planner)",null,"Appro ved",{"$nulls":5},"CDD\napproval on 11/16/20\n22","8/12/2\n022","11/27/\n2022","Jocilene Morones","jocilenem9@gmail.com","(714)\n809-\n8564"]
["Lomita","5242 E\nLomita Ave","9286\n9","Das Residenc e Lot 1","Construction of single family residence on hillside","Vidal F. Márquez","Pendi ng",null,null,"Pending",null,null,null,"Comment letter provided 02-26-21.\nUnder\nReview.","11/10/\n2020","2/23/2\n023","Hugo Soria","hugosoriadesign@yaho o.com"]
["Lomita","5212 E\nLomita Ave","9286\n9","Das Residenc e Lot 4","Construction of single family residence on hillside","Vidal F. Márquez","Pendi ng",null,null,"Pending",null,null,null,"Comment letter provided 02-26-21.\nUnder\nReview.","11/10/\n2020","2/23/2\n023","Hugo Soria","hugosoriadesign@yaho o.com"]
["Main","231 N\nMain St","9286\n8","Aldrich Residnce ADU","Construct a new detached ADU with a partial\nconversion of","Tiffany Chhan",null,"Pendi ng",{"$nulls":5},"Applicant withdrawi ng applicatio\nn?",null,"4/28/2\n022","Tom Aldrich","taldrich@dseainc.com","(714)\n639-\n3958"]
[{"$nulls":4},"an existing garage"]
["Main","1562 N\nMain St","9286\n7","Phoenix Club SCE Tower Wireless Facility","Proposed wireless facility mounted on an SCE high- power transmission tower.\nConsists of one (1) panel\nantenna and 2 RRUs per sector, and necessary ancillary radio equipment under the tower on an enclosed 5' by\n7' concrete\npad.","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"11/1/2\n022","CDD\napproved on 11/1/22",null,"2/23/2\n023","Brian De La Ree","BDeLaRee@core.us.co m","(323)\n273-\n2199"]
["Main","1234 N\nMain St","9286\n7","Imperial Stations","Convert existing car wash to express car wash and construct 800- SF addition to existing convenience\nstore","Vidal F. Márquez","Appr oved",null,null,"Approved","Approve d",null,"3/21/2\n022","PC\nApproved 3/21/202\n2","4/17/2\n018","2/23/2\n023","Fred Cohen","fcohen@cjccorp.com"]
["Main","170 S\nMain St","9286\n8","CHOC\nAutism Center Fencing","Construct security fencing for the CHOC Autism\ncenter","Tiffany Chhan","Appr oved","Appro ved",{"$nulls":4},"7/12/2\n022",null,null,"8/4/20\n22","Michael K. Schafer","mschafer@msa- corp.net","(949)\n584-\n5426"]
["Main","763 S\nMain St","9286\n8","Stagecoa ch Orange","Request for an ABC Type 47 License for a proposed\nresturant.","Vidal F. Márquez",{"$nulls":4},"Pending",null,null,"Comment letter sent 3/9/23.","2/24/2\n023","3/9/20\n23","Heinrich Stasiuk","heinrich@wildthymegr oup.com","(602)\n427-\n7123"]
["Main","742 E\nMain St","9286\n5","John C. Marvick","New two story CMU office building with associated site improvements for a roofing\ncontractor","Chad Ortlieb","Appr oved",null,null,"Approved",null,null,"7/7/20\n22","DRC\napproved 7/7/2022","9/20/2\n021","2/23/2\n023","John C. Marvick","jcmarvick@sbcglobal.n et"]
["Maple","137 E\nMaple\nAve","9286\n6","Orange Plaza Inn","A proposal to convert an existing building to a 12 room hotel with ancillary meeting space\nand amenities.","Historic Preservat\nion","Appr oved",null,null,"Approved","Approve d",null,"11/16/\n2020","SMART 09-21-20\n(rec. approval), DRC 10-\n07-20\n(rec. approval), PC 11-16-\n20\n(approved\n)",null,"11/9/2\n021","Ajja Investmen\nts","ajjainvestments@live.c om"]
["Maple","621 E\nMaple\nAve","9286\n6","Maple Ave ADU","New detached 800 SF ADU on\na single family residential\nproperty.","Ani Mnatsak\nanyan",null,"Pendi ng",{"$nulls":6},"1/10/2\n023","2/10/2\n023","Ming Huo","hm9808@gmail.com","(626)\n500-\n5977"]
["Maple","623 E\nMaple\nAve","9286\n6","Maple Ave Unit\nRemodel","Remodel of an existing unit including building height increase and relocation of\nentry area.","Ani Mnatsak\nanyan",null,null,null,"Pending",{"$nulls":4},"1/31/2\n023",null,"Ming Huo","hm9808@gmail.com","(626)\n500-\n5977"]
["Maple","3138 E\nMaple Ave","9286\n9","The Knolls Homewor k House","New recreational room, office,\nand restroom for an existing","Vidal F. Márquez","Pendi ng","Pendi ng",{"$nulls":5},"Incomplet e Letter sent 3/2/2023","12/15/\n2022","3/9/20\n23","Matt Aulicino","aulicno@auxoffice.com","(213)\n568-\n3578"]
[{"$nulls":4},"apartment complex."]
["Maple","1127 W\nMaple Ave","9286\n8","Rosenzwi g ADU","A proposal to construct a new 496 square foot detached 1\nbedroom, 1\nbathroom ADU","Ryan Agbayani",null,"Appro ved",{"$nulls":5},"12/13/22\n- Began initial review of plans.\nEmail sent to applicant requestin g PDF of plans and site photos.\n12/20/22\n-\nIncomplet e letter and redlines emailed to applicant. 1/24/23 - CDD\napproval letter emailed to\napplicant.","11/28/\n2022","12/20/\n2022","Steve Rosenzwei g","steven_rosenzweig200 2@yahoo.com","(714)\n928-\n2804"]
["Marie","229 S\nMarie Pl","9286\n8","Do Detached ADU","New 964 SF\ndetached ADU consisting of two bedrooms\nand two baths","Monique Schwartz",null,"Appro ved",{"$nulls":5},"CDD\napproved 1/10/202\n3",null,"1/18/2\n023","An Ha","info@fgdesignlab.com","(714)\n465-\n4337"]
["Mayfair","209 E\nMayfair Ave","9286\n7","Mayfair Remodel","Remodel existing one- story SFD and construct new addition (1,576 SF) at\nrear of property to add one bedroom and two\nbathrooms","Ryan Agbayani",null,"Withd rawn",{"$nulls":5},"10/4/22 -\nIncomplet e letter emailed to applicant. 10/10/22\n-\nApplicant resubmitt ed revised plans.\n10/11/22\n- Planning emailed correction s to applicant. 11/4/22 -\nApplicant sent email to withdraw ADR\napplicatio\nn. They reduced the scope of work to be less than 50% of the existing dwelling. Project will proceed straight to building plan check.\nPlanning",null,"10/10/\n2022","Fahim Boulos","f.boulos@ymail.com","(949)\n616-\n8494"]
[]
[{"$nulls":13},"counter comment s provided. 11/9/22 -\nApplicant submitted plans with reduced scope of work, which was routed straight to building plan check."]
["Mayfair","303 E\nMayfair Ave","9286\n7","Huber ADU","New detached 978 SF ADU\nwith two bedrooms","Monique Schwartz",null,"Pendi ng",{"$nulls":7},"10/24/\n2022","Phillip Bennett","bpbarchitect@aol.com","(714)\n997-\n4956"]
["Mayfair","311 E\nMayfair Ave","9286\n7","Hamilton Addition","Proposed 823 SF addition to an existing 1,065 SF\nexisting single family residence.","Vidal F. Márquez",null,"Pendi ng",{"$nulls":5},"Incomplet e Letter sent 2/10/202\n3","1/5/20\n23","3/9/20\n23","Edward Osuch","patricia@neo-inc.com","(213)\n257-\n4611"]
["Meats","340 W\nMeats\nAve","9286\n5","A & M Tree Specialist\nCorp","Construction yard for a tree trimming company including the parking of company vehicles and\nequipment.","Chad Ortlieb","Pendi ng",null,null,"Pending","Pending",null,null,null,"12/22/\n2022",null,"Ross McCune","ross@caistealbuilders.c om","(714)\n478-\n4894"]
["Milford","2308 N\nMIlford St","9286\n7","Nhu ADU","Construction of a new detached 749 square foot ADU.","Ray Pascua (Contract Planner)",null,"Pendi ng",{"$nulls":5},"Comment s letter sent to applicant on 11/2/202\n2 and then to the property owner on 1/27/202\n3","8/16/2\n022","11/27/\n2022","Loc Ly","locly1000@yahoo.com","(714)\n567-\n2765"]
["Monter ey","141 N\nMonter ey Rd","9286\n6","Harris Addition","New first floor and second floor addition to an existing two-story\nresidence.","Ryan Agbayani",null,"Pendi ng",{"$nulls":5},"1/4/23 -\nIncomplet e letter emailed to applicant.","11/28/\n2022",null,"Ramon Sanchez","cbhome626@gmail.co m","(626)\n279-\n5657"]
["Montgo mery","4632 E\nMontgo mery Pl","9286\n9","Zojaji Residenc e","Construction of a new single-family\ndwelling","Ray Pascua (Contract\nPlanner)","Pendi ng","Appro ved",{"$nulls":5},"Approved",null,"11/27/\n2022","Mohsen Zojaji","zojajim@yahoo.com","(949)\n463-\n1552"]
["Montgo mery","4638 E\nMontgo\nmery Pl","9286\n9","Zojaji Residenc\ne","Construction of a new single-family\ndwelling","Ray Pascua (Contract\nPlanner)","Pendi ng","Appro ved",{"$nulls":5},"Approved","5/24/2\n022","11/27/\n2022","Mohsen Zojaji","zojajim@yahoo.com","(949)\n463-\n1552"]
["Noble","455 N\nNoble St","9286\n9","Beardon ADU","Construciton of a new detached 642\nsquare foot ADU","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"8/26/2\n022","Under plan check","6/15/2\n022","2/23/2\n023","Samuel Kim","skim- inkdesign@yahoo.com","(213)\n383-\n7730"]
["Oak","6807 N\nOak Ln","9286\n9","Pop Accessory Building","Construct a 1,177 sf, two story accessory building consisting of 450 sf - 2\noffices and 2 bathrooms and a 727 sf\ngarage","Vidal F. Márquez","Pendi ng","Pendi ng",{"$nulls":5},"Comment Letter scheduled for 1/25/202\n3","9/12/2\n022","3/9/20\n23","Dan Cojocnean","muscatoto@yahoo.com","(714)\n669-\n3870"]
["Oak","230 S\nOak Ln","9286\n9","Multifami ly and ADU\nPrelim","Preliminary review of a proposed multifamily and ADU development\nona vacant lot.","Monique Schwartz","Pendi ng",{"$nulls":7},"12/12/\n2022","1/26/2\n023","Paymon Roshan","hyfainc@hotmail.com","(714)\n448-\n8629"]
["Oakwo od","828 S\nOakwo od St","9286\n9","Bhullar Residenc e Addition","Proposal for residential addition to a contributing property in the Eichler Fairhaven Historic\nDistrict","Anna Pehoush ek",null,null,null,"Approved",null,null,null,"Continued by DRC 6/15/22;\napproved\non 9/12/22.",null,"9/27/2\n022","Jeff Fracker","constfrack@gmail.com"]
["Olive","114 N\nOlive St","9286\n6","Blueston e Lane Alcohol Permit","A request to serve beer and wine in association with an existing restaurant in\nOld Towne","Ani Mnatsak anyan",{"$nulls":4},"Hearing Date 4/19/20\n23",null,null,"Routed for review to PD on 9/13/22","8/17/2\n022","1/10/2\n023","Eddie Navarette","matthew@fedesignand consulting.com","(213)\n687-\n6963"]
["Olive","331 N\nOlive St","9286\n6","331 N.\nOlive ADU","A request to construct an 800 square foot one bedroom\ndetached ADU","Ani Mnatsak anyan",null,"Appro ved",{"$nulls":4},"2/28/2\n023",null,"12/1/2\n022","12/5/2\n022","331 N.\nOlive St. Holding LLC","mark@stack-llc.com","(310)\n803-\n6510"]
[{"$nulls":4},"on a property with an inventoried structure in the Old Towne\nDistrict"]
["Olive","866 N\nOlive St","9286\n7","Trujillo ADU","Converting existing detached garage and expanding footprint for a\nnew 565 ADU.","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"12/6/2\n022","CDD\nApproved","10/24/\n2022","2/15/2\n023","Tomasa Trujillo",null,"(714)\n906-\n0094"]
["Orange Olive","2101 N\nOrange Olive Rd","9286\n5","I & B Corp","98 SF addition for remodel retail store existing gas\nstation","Vidal F. Márquez","Appr oved",null,null,"Approved",null,null,"4/20/2\n022","Under contructio n",null,"2/23/2\n023"]
["Orange","144 N\nOrange St","9286\n6","Archtects Orange Sign Program","Proposed sign program for a Plaza historic multi-tenant\nbuilding.","Historic Preservat ion",null,null,null,"Approved",null,null,"6/15/2\n022",null,null,"6/28/2\n022","Barbara Cohen","bcohen@ad-s.com","(800)\n862-\n3202"]
["Orange","829 N\nOrange St","9286\n7","Paino ADU","Detached garage conversion into a 522 SF ADU","Ryan Agbayani",null,"Appro ved",{"$nulls":5},"1/5/22 - CDD\nApproval Letter emailed to applicant.",null,"10/7/2\n022","Shirey Ann Paino","shirleypaino@gmail.co m","(714)\n264-\n8040"]
["Orange wood","1940 W\nOrange wood Ave","9286\n8","La Linda Plaza Senior Apartme nts","Conversion of a commerical office building complex into a 52-unit market rate senior apartment\ncomplex.","Monique Schwartz","Pendi ng",null,null,"Pending","Pending",null,null,"Revised plans received 1/3/2023",null,"1/26/2\n023","Sean Suselo","suselo@aol.com","(714)\n925-\n2525"]
["Palm","732 E\nPalm Ave","9286\n6","Sukeena Residenc e","Request for a front yard wall in the Old Towne Historic\nDistrict","Historic Preservat ion",null,null,null,"Pending",null,null,null,"DRC 07-\n21-21\n(cont.)",null,"11/9/2\n021","Gwen Sukeena",null,"(949)\n439-\n0505"]
["Palm","1139 E\nPalm Ave","9286\n6","Resnick ADU","Construct a new detached 618 SF ADU\nand garage expansion","Ray Pascua (Contract Planner)",null,"Appro ved",{"$nulls":4},"1/12/2\n023","CDD\napproval on 1/12/202\n3","10/21/\n2022","11/27/\n2022","John Johnston","jjohnstone@allproremo deling.com","(714)\n288-\n1314"]
["Palm","2461 W\nPalm\nAve","9286\n8","Sneed ADU","New detached 476 SF ADU","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"1/24/2\n023","Approved","12/21/\n2022","2/15/2\n023","Chia Chi Chang","nicole201245@gmail.co m","(949)\n423-\n4651"]
["Palmyr a","815 E\nPalmyr a Ave","9286\n6","Tina Herman","Request to construct an addition to a historic single- family residence and relocate a\ngarage","Historic Preservat ion"]
["Palmyr a","2205 E\nPalmyr\na Ave","9286\n9","Kornersto ne Muslim\nCemetery","Request to establish a\ncemetery","Vidal F. Márquez","Appr oved",null,null,"Denied","Pending","Pendi ng",null,"DRC\nrecomme nded denial to the Planning Commissi on on 7/20/22. CEQA\nConsultan t reviewing public comment\ns.",null,"9/26/2\n022","Abdul Saquib","asaquib@cmdonline.co m","(310)\n948-\n6885"]
["Palmyr a","905 E\nPalmyr a Ave","9286\n6","Nash ADU","Add an ADU attached to an existing \"barn\"\nstructure.","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"11/22/\n2022",null,"8/2/20\n22","2/23/2\n023","Bryan & Lorie Nash","bryan@benashinc.com","(714)\n747-\n1249"]
["Palmyr a","206 W\nPalmyr a Ave","9286\n6","Wencel Residenti al Addition","Residential remodel including a shed roof expansion at the rear and new detached\nshed","Ani Mnatsak anyan",null,null,null,"Pending",null,null,null,"Comment letter sent 11/8/22","10/12/\n2022","11/16/\n2022","Ali Haddad","ali@prosperarch.com","(657)\n223-\n6828"]
["Parker","681 S\nParker St","9286\n8","Alessi - Office Complex Landscapi ng","A proposal to renovate existing landscaping at an existing office\ncomplex.","Monique Schwartz","Appr oved",null,null,"Approved",null,null,"8/19/2\n020",null,null,"9/28/2\n022","Diego Alessi","diegoa@aoarchitects.c om","(714)\n639-\n9860"]
["Pepper Wood","1630\nPepper Wood Cir","9286\n9","Adediran Residenc e","Request to construct a habitable accessory structure in\nrear yard.","Vidal F. Márquez","Pendi ng",null,"Pendi ng",{"$nulls":4},"Inactive",null,"9/29/2\n022"]
[]
["Pine","374 N\nPine St","9286\n7","McBride & Lui Residenc\ne","Expansion of a legal nonconformin\ng duplex","Ani Mnatsak anyan",null,null,null,"Pending",null,null,null,"Comment letter sent 11/8/22","10/13/\n2022","11/9/2\n022","Cherie Lui","cherie.lui@gmail.com","(714)\n617-\n0774"]
["Pine","553 N\nPine St","9286\n7","England ADU","Remove a non- permitted structure and convert an existing detached garage to an ADU and construct an addition onto the rear of the garage to create a 750 square foot\nADU.","Alvin Nuval (Contract Planner)",null,"Pendi ng",{"$nulls":6},"8/12/2\n022","8/15/2\n022","Tom Aldrich","taldrich@dseainc.com"]
["Pine","367 S\nPine St","9286\n6","Sodetani ADU","A new one story detached 636 square foot ADU on a non- contributing property in the Old Towne Historic\nDistrict.","Monique Schwartz",null,"Appro ved",{"$nulls":4},"8/1/20\n22","In the historic\ndistrict",null,"1/18/2\n023","Oscar Vega","oscar.vega@vecodesign s.com","(714)\n499-\n1247"]
["Pinewo od","3218 N\nPinewo od St","9286\n5","Gjesdal ADU","A proposal to construct a new 580 square foot detached 1\nbedroom, 1\nbathroom ADU","Ryan Agbayani",null,"Appro ved",{"$nulls":5},"12/20/22\n- CDD\napproval letter issued to applicant.","11/23/\n2022","11/30/\n2022","Nathan Gjesdal","nategjesdal@hotmail.c om","(714)\n944-\n5536"]
["Plaza","71\nPlaza Square","9286\n6","AT&T\nNSB Site \"CLL0115 7\"","A request to establish a rooftop stealth screen wireless facility in the Old Towne Historic\nDistrict","Alvin Nuval (Contract Planner)","Pendi ng",null,null,"Pending",{"$nulls":4},"5/31/2\n022","5/31/2\n022","Adrian Culici","adrian.culici@eukongro up.com","(949)\n648-\n6995"]
["Pointse ttia","321 S\nPoinset tia Dr","9286\n8","Pilapande t ADU","A request to construct a new detached 734 square foot ADU","Ray Pascua (Contract Planner)",null,"Pendi ng",{"$nulls":5},"Received responses to comment s and revised plans 02-\n21-23","8/15/2\n022","11/27/\n2022","David Hung Le","brightark@gmail.com","(714)\n868-\n2499"]
["Poplar","749 N\nPoplar St","9286\n8","TCS Bus","Bus Storage on\npaved parking lot","Vidal F. Márquez","Pendi ng",null,null,null,"Pending",null,null,"Expired",null,"9/29/2\n022"]
["Ranch Wood","777\nRanch Wood Trl","9286\n9","Philip Bennett","Garage expansion where the garage door exceeds eight\nfeet in height","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"10/19/\n2021","Under constructi on",null,"9/29/2\n022"]
["Rancho Santiag o","647 N\nRancho Santiag\no Blvd","9286\n9","Rancho Ridge Subdivisi\non","Preliminary review of a proposed subdivision of a 1.93 acre parcel to create fourteen 6,000 square foot lots with single-family\nresidences.","Tiffany Chhan","Com plete",{"$nulls":6},"Preliminar y review complete. No formal review of project has been submitted\n.",null,"6/17/2\n022","David Blumenth al","dblumenthal@sagecres tplanning.com","(714)\n313-\n3713"]
["Ridgelin e","938 N\nRidgelin\ne Rd","9286\n9","Diaz Residenc\ne ADU","Construct a new 2 bedroom and 1 bathroom\nADU","Tiffany Chhan",null,"Appro ved",{"$nulls":4},"7/28/2\n022",null,null,"8/4/20\n22","Michael Margerum","mikemargerum@aol.co m"]
["River","338 E\nRiver Ave","9286\n6","Kreutel/ Marquez Residenc e\nAddition","Addition to existing single story dwelling with a partil\ndemolition.","Ani Mnatsak anyan",null,null,null,"Approved",null,null,null,"DRC Date: 11/16","5/20/2\n022","5/20/2\n022","Daniel B Kreutel","dkreutel@sbcglobal.net","(714)\n288-\n1424"]
["San Miguel","2632 N\nSan Miguel Dr","9286\n7","Houshiar ADU","Construction of a new detached 736 square foot ADU and 480 square foot\nroof deck.","Emily Golubow",null,"Pendi ng",{"$nulls":6},"8/16/2\n022","8/22/2\n022","Oscar Vega","oscar.vega@vecodesign s.com","(714)\n499-\n1297"]
["Santa Cecelia","4171 N\nSanta Cecelia St","9286\n5","Dao Residnec e","Addition of 800 square feet onto a\nsingle-family dwelling","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"10/25/\n2022","Under plan check","6/6/20\n22","2/23/2\n023","Jason Gettlew","jason@gettlergc.com","(714)\n316-\n4956"]
["Santiag o","2860 N\nSantiag o Blvd","9286\n7","H&S Energy","A proposal to construct solar carports within the existing parking lot of an office\nbuilding","Tiffany Chhan","Pendi ng","Pendi ng",{"$nulls":7},"4/1/20\n21","Jesse Barraza","jbarraza21@gmail.com","(562)\n441-\n8063"]
["Santiag o","2640 N\nSantiag o Blvd","9286\n7","Design Concepts","A proposal to remodel to an existing service station, addition to existing convenience store, and new automatic drive through\ncar wash.","Monique Schwartz","Appr oved",null,null,"Approved","Approve d",null,"11/15/\n2021",null,null,"9/28/2\n022","Shiv Talwar","dsignconcepts@yahoo. com","(909)\n591-\n3939"]
["Santiag o Canyon","1700 E\nSantiag o Canyon Rd","9286\n9","Santiago Hills II Planned Communi ty","A request for approval of tentative tract maps and modified Planned Community standards and design guidelines for a 1,180 unit residential subdivision in the Santiago Hills II Planned Community. A modified Runoff Management Plan (ROMP) and modified Development Agreement are also included in this request. (This request is a modification to a\npreviously- approved project. The previous approvals allow for a maximum of 1,746 units in Santiago Hills\nII).","Ryan Agbayani","Appr oved",null,null,"Approved","Approve d","Appr oved",null,"Address is for reference location only.\nGeneral project location is at the intersecti on of Jamboree Road and Chapman Avenue Various Approval dates. No current\nactivity",null,"11/18/\n2022","Jamie Yoshida","jyoshida@irvinecompa ny.com","(949)\n720-\n2702"]
[]
["Santiag o Canyon","6145 E\nSantiag o","9286\n9","SB 330 -\nCreekside Village","Preliminary Review\napplication for a development","Robert Garcia","Com plete",{"$nulls":6},"SRC\ncomment s comment","2/9/20\n23",null,"Christoph er Nichelson","chris@milancap.com","(714)\n687-\n0000"]
[null,"Canyon Rd",null,null,"consisting of 200 detached units.",{"$nulls":8},"letter sent on 03/09/20\n23."]
["Santiag o Canyon","6500 E\nSantiag o Canyon Rd","9286\n9","Salem Lutheran Church & School Temporar y Modular Building Time\nExtension","A requested one-year time extension for a temporary 12’\nx 32’ modular building.","Ray Pascua (Contract Planner)",null,null,"Appr oved",null,null,null,"9/21/2\n022","Approved","8/12/2\n022","11/27/\n2022","Julie Beckman","jbeckman@salemorang e.com","(714)\n922-\n1065"]
["Santiag o Canyon","6500 E\nSantiag o Canyon\nRd","9286\n9","Salem Lutheran Church & School Modular\nBuildings","A request to construct two modular buildings (20 ‘\nx 50’ and 20’ x\n30’) located near the parcel’s northern boundary replacing three storage containers presently on site. On unit will serve youth programs and the other will\nbe for storage.","Vidal F. Márquez","Appr oved",null,null,"Pending",null,null,null,"Scheduled for 3/15/202\n3 DRC\nHearing","8/22/2\n022","2/23/2\n023","Julie Beckman","jbeckman@salemorang e.com","(714)\n922-\n1065"]
["Santiag o\nCanyon","7845 E\nSantiag o Canyon\nRd","9286\n9","Holy Sepulcher\nCemetery","A proposal to construct a new cemetery maintenance\nfacility","Monique Schwartz","Appr oved",null,null,"Approved","Approve d",null,"10/19/\n2020",null,null,"9/28/2\n022","Roman Catholic Dioceses of Orange, Mike\nWesner",null,"(714)\n370-\n9778"]
["Santiag o Canyon","7536 E\nSantiag o Canyon Rd","9286\n9","Dang Residenc e","A proposal to construct a new one-story single-family dwelling (3,380 square- feet) with an attached 2-car garage (587 square-feet) on a legally subdivided, 24,302 square-\nfoot, or 0.56- acre vacant parcel","Ryan Agbayani","Pendi ng","Pendi ng",{"$nulls":5},"3/15/23 - CDD\nsigned the plans.",null,"3/15/2\n023","Tim Nguyen","timothy@moriestudioa rch.com","(949)\n395-\n1718"]
["Shaffer","159 N\nShaffer\nSt","9286\n6","Malloy Residenc\ne","A proposal to demolish an existing non- contributing garage and replace it with a new 400 SF garage with 661AF\nattached ADU.","Ani Mnatsak\nanyan",null,null,null,"Continued",null,null,null,"Comment letter sent 11/29/20\n22",null,"4/11/2\n022","Michelle and Ryan\nMalloy","mnmorange@gmail.co m"]
["Shaffer","325 N\nShaffer\nSt","9286\n6","McCullou gh Residenc\ne","A proposal to demolish an existing 118 SF rear addition and construct a new 317 SF\naddition.","Ani Mnatsak\nanyan",null,null,null,"Approved",null,null,"10/19/\n2022","DRC Date: 10/19",null,"6/3/20\n22","Doug Ely","dely@desainc.com","(714)\n639-\n3958"]
["Shaffer","945 N\nShaffer St","9286\n7","Selman Residenc e","Construction of 653 sq. ft. outdoor kitchen and\npool house.","Vidal F. Márquez","Appr oved","Appro ved","Appr oved",null,null,null,"10/15/\n2019","Under contructio n",null,"9/29/2\n022"]
["Shaffer","1746 N\nShaffer\nSt","9286\n5","Accorner o Units","Demolish an existing residence, split the lot via a parcel map, and construct two mirror image single- family dwellings on the resulting lots. Reference expired approved case nos.: DRC 4891, MNSP\n0808, MNSP\n0874, and TPM\n0006","Chad Ortlieb","Pendi ng",null,null,"Pending",{"$nulls":4},"7/19/2\n022","7/20/2\n022","Acres, Howard E.\nGlasser","heg928@pacbell.net","(714)\n553-\n5210"]
["Shaffer","454 S\nShaffer St","9286\n6","Johnston Artificial Turf","A request to allow artificial turf, versus alternative allergen free landscaping, in the Old Towne District due to an allergic reaction to\ngrass.","Monique Schwartz",{"$nulls":9},"9/28/2\n022","Matthew Johnston","matt_johnston54@yah oo.com","(949)\n733-\n7477"]
["Silverle af","4818 E\nSilverle af Ave","9286\n9","Whitney Residenc e","New single story addition to an existing single story\nresidence.","Monique Schwartz",null,"Appro ved",{"$nulls":4},"11/1/2\n021",null,null,"9/28/2\n022","Darin Whitney",null,"(714)\n357-\n2167"]
["Simmo ns","4628 W\nSimmo ns Ave","9286\n8","Ruiz ADU","Convert an existing garage\ninto a JADU","Tiffany Chhan",null,"Appro ved",{"$nulls":4},"7/29/2\n022",null,null,"8/4/20\n22","Massieh Kabir","mossykabir@gmail.com","(949)\n677-\n0965"]
["Spinnak er","291 N\nSpinnak er St","9286\n8","Spinnaker ADU","Detached 797\nsquare foot, 2\nbedroom, 1 bathroom ADU and 188 square foot room addition to the existing home and a 188 square\nfoot patio","Monique Schwartz",null,"Appro ved",{"$nulls":4},"2/6/20\n23","CDD\nApproval Letter sent\n2/6/2023","7/18/2\n022","2/10/2\n023","Kevin Le","kevin.ink.inc@gmail.co m","(508)\n826-\n5451"]
["Stearns","3001 E\nStearns St","9286\n9","Pack ADU","Convert existing detached garage into a\n480 SF ADU.","Emily Golubow",null,"Pendi ng",{"$nulls":5},"Sent initial comment letter to contact on\n3/9/23.","2/10/2\n023",null,"R. Adam Dorn","r.adamdorn@gmail.co m","(714)\n400-\n2569"]
["Struck","534 W\nStruck Ave","9286\n7","Prologis","Demolition of existing building and construction of a new 57,000 SF\nwarehouse building for a truck terminal and 5,400 SF maintenance\nbuilding","Robert Garcia","Appr oved",null,null,"Approved","Pending","Pendi ng",null,"SMART\nRecomme ndation 09-08-21, DRC\nRecomme ndation 02-16-22,",null,"2/22/2\n023","Byanka Velasco","byanka.velasco@webba ssociates.com","(951)\n320-\n6001"]
["Sycamo re","813 E\nSycamo re Ave","9286\n6","Sycamore ADU","A request to construct a new 740 square foot, detached 2\nbedroom, 2 bathroom ADU","Tiffany Chhan",null,"Appro ved",{"$nulls":4},"9/20/2\n022",null,null,"9/20/2\n022","Mark Prather","mprather@m1m.com","(714)\n709-\n3787"]
["The City","840 S\nThe\nCity Dr","9286\n8","Street Lights Residenti\nal","A proposal to redevelop an existing commercial property with a 6-story, 225 unit multifamily and commercial building over three-story subterranean parking and one detached parking deck on adjacent parcel, as part of a mixed use\ndevelopment.","Monique Schwartz","Appr oved",null,null,"Approved","Pending",null,null,"Pending revised responses to comment\ns on MND",null,"1/18/2\n023","Scott Levy","slevy@streetlightsres.c om","(619)\n344-\n2544"]
["The City","451 S\nThe City Dr","9286\n8","Reliant Land Services","New wireless facility","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"5/25/2\n022","Permit issued","2/23/2\n022","2/23/2\n023","Robert Schultz","robert.schultz@rlsusa.c om"]
["The City","3520 E\nThe City\nWay","9286\n8","In N Out","Proposed demolition of an existing sit down restaurant for the construction of a new fast food drive through\nrestaurant.","Robert Garcia","Appr oved",null,null,"Approved","Approve d",null,null,"SRC\nRecomme ndation 8/31/22, DRC\nRecomme ndation 11/02/20\n22, PC\nApproved 12/05/20\n22",null,"2/22/2\n023","Katie Sanchez","ksanchez@innout.com","(626)\n260-\n2937"]
["Town and Country","702 W\nTown and Country Rd","9286\n8","Town and Country Apartme nts and\nTownho mes","A proposal to redevelop a 12 acre office complex with\n727 multi- family units","Monique Schwartz","Appr oved",null,null,"Approved","Approve d","Appr oved","6/12/2\n018",null,null,"1/18/2\n023","Trevor Bouche","trevorb@ffres.com","(760)\n855-\n5572"]
[{"$nulls":4},"(653\napartments, and 74 townhomes)"]
["Town and\nCountry","1100 W\nTown and Country\nRd","9286\n8","Distribute d Solar Develop\nment","A proposal to install a solar panel canopy on top of existing parking\nstructure","Vidal F. Márquez","Appr oved","Appro ved",{"$nulls":4},"9/9/20\n22","Permit issued","2/11/2\n023","9/29/2\n022","Christian Inzunza","Christian.Inzunza@dsdr enewables.com","(760)\n902-\n2314"]
["Tracy","335 S\nTracy\nLn","9286\n9","Ocampo Residenc\ne","A proposal for a 1,242 sq. ft. room addition and new detached two\ncar garage.","Monique Schwartz",null,"Appro ved",{"$nulls":4},"7/23/2\n019",null,null,"2/10/2\n023","Al Maciel",null,"(949)\n283-\n0877"]
["Tustin","387 N\nTustin\nSt","9286\n7","Orange Express\nCar Wash","Modification of an existing full service car wash to an express car\nwash.","Monique Schwartz","Appr oved",null,null,"Approved","Approve d",null,"9/9/20\n20",null,null,"9/28/2\n022","Kyong Suk Kim",null,"(213)\n800-\n3639"]
["Tustin","2191 N\nTustin\nSt","9286\n5","Target Expansio\nn","A request to convert an existing garden center to an enclosed building\naddition.","Monique Schwartz","Appr oved",null,"Appr oved","Approved",null,null,"9/16/2\n020",null,null,"1/26/2\n023","Justin Becker",null,"(619)\n744-\n0169"]
["Tustin","214\nand 216 N\nTustin St","9286\n7","Jim's Original Restaura nt","New 2 story building; a drive through restaurant with outdoor dining area on the first floor; a second floor\noffice.","Ryan Agbayani","Appr oved",null,null,"Approved","Approve d",null,"1/16/2\n023","1/16/22 - PC\napproved project with modified condition\ns","7/1/20\n22","9/26/2\n022","Pedram Shokati","pedrams@AOarchitects\n.com","(714)\n639-\n9860"]
["Tustin","2191 N\nTustin St","9286\n5","Target Canopy Structure","Proposal for a canopy structure and signage for drive up pick\nup customers.","Vidal F. Márquez","Pendi ng","Pendi ng",{"$nulls":5},"Comment letter sent 11/18/22","3/29/2\n022","2/6/20\n23"]
["Tustin","2200 N\nTustin\nSt","9286\n5","SB 330 -\nResidenc es at the Village at\nOrange","Preliminary Review application for a proposed residential development on 14.29 acres within the existing Village at Orange mall that will include 297 for sale condominiums\n, 75 below market rate accessory dwelling units with kitchenette for a total of 372 units, a 28,000 square foot recreation center, and a 1,500 square foot restroom and community\nmeeting room.","Chad Ortlieb","Occu red",{"$nulls":6},"SRC\noccured\n2-8-23","1/25/2\n023","2/13/2\n023","Peter Vanek","pvanek@integralcomm unities.com","(949)\n307-\n3482"]
["Tustin","2375 N\nTustin St","9286\n5","Best Buy Facade Remodel","Facade remodel of the existing Best\nBuy.","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"3/1/20\n23",null,"1/16/2\n023","3/8/20\n23","Bickel Group Architectu\nre"]
["Tustin","432 N\nTustin St","9286\n7","Motorcyc le Wheel Works","Request to establish a motorcycle accessories sales and installation\nbusiness.","Vidal F. Márquez",{"$nulls":4},"Pending",null,null,"Under review","6/21/2\n022","2/6/20\n23","Severino Navera","mnavera@hotmail.com","(714)\n473-\n2656"]
["Tustin","584 N\nTustin St","9286\n7","Popeye’s Chicken","A request to construct a new drive- through\nrestaurant.","Vidal F. Márquez","Appr oved",null,null,"Approved","Approve d",null,"9/8/20\n21","Under Plan Check","1/29/2\n021","2/23/2\n023","Petrossi & Associates\n, Inc.","hp@petrossiassoc.com"]
["Tustin","607 N\nTustin St","9286\n7","Root Vision Endo","Facade remodel of an existing building for a\ndentist office.","Ray Pascua (Contract Planner)",{"$nulls":7},"CDD\napproval letter 02-\n09-23",null,"11/27/\n2022","Kyle Ng","kyle.ng@boaarchitectur e.com","(652)\n912-\n7900"]
["Tustin","2375 N\nTustin St","9286\n5","Best Buy Facade Remodel","Facade remodel of the existing Best\nBuy.","Vidal F. Márquez",null,"Appro ved",{"$nulls":4},"3/1/20\n23","CDD\nApproved 3/1/2023","1/16/2\n023","3/1/20\n23","Stephan Thorp","sthorp@burnhamuse.c om","(949)\n760-\n9150"]
["Tustin","2575 N\nTustin St","9286\n5","Chick-fil- A Drive- Thru Modificat\nion","A proposal to modify the existing site plan configuration to add a second drive\nthru lane.","Vidal F. Márquez","Appr oved","Appro ved",null,"Approved",null,null,"9/8/20\n22","Under constructi on","3/2/20\n22","2/6/20\n23"]
["Univers ity","1\nUnivers ity Dr","9286\n6","Chapman Universit y Specific Plan Amendm\nent #7","A proposal to update the Chapman University\nSpecific Plan.","Anna Pehoush ek","Pendi ng",null,null,"Pending","Pending","Pendi ng",null,"Awaiting submittal of draft EIR for\nreview",null,null,"John Moreland","jmoreland@ktgy.com"]
["Van Bibber","545 E\nVan Bibber\nAve","9286\n6","Sargeant Additon","Addition of a 169 square foot bathroom off of the primary\nbedroom,","Ani Mnatsak anyan",null,null,null,"Pending",{"$nulls":5},"6/17/2\n022","Aimee Ho","henry.sargeant@gmail. com","(714)\n757-\n1753"]
[{"$nulls":4},"extending into the rear yard."]
["Village","1500 E\nVillage\nWay","9286\n5","SB 330\nResidenc es at the\nVillage","Proposed residential development on 14.29 acres within the existing Village at Orange mall that will include 297 for sale condominiums\n, 75 below market rate accessory dwelling units with kitchenette for a total of 372 units, a 28,000 square foot recreation center, and a 1,500 square foot restroom and community\nmeeting room.","Chad Ortlieb",{"$nulls":8},"1/25/2\n023",null,"Peter Vanek","pvanek@integralcomm unities.com","(949)\n307-\n3482"]
["Village","1500 E\nVillage Way","9286\n5","Riviera Medical COVID-19\nTesting","Proposal to operate a COVID-19\ntesting stie behind the Village at Orange; not associated with any\nmedical","Tiffany Chhan","Pendi ng",null,"Pendi ng",{"$nulls":4},"Incomplet e letter sent on 9-\n12-22","8/15/2\n022","9/21/2\n022","Riviera Medical Corporati on/Patty Powell","patty@orangecountyco vidclinic.com","(970)\n844-\n7667"]
[{"$nulls":4},"provider on- site."]
["Vista Bluff","2690 N\nVista Bluff Rd","9286\n7","Bjaradwaj ADU","New attached ADU","Tiffany Chhan",null,"Appro ved",{"$nulls":4},"9/23/2\n022",null,null,"9/23/2\n022","Jayant Bharadwa\nj","jbharadwaj@mac.com","(714)\n726-\n8069"]
["Culver","638 W\nCulver Ave","9286\n8","Long Doan ADU","429 square foot interior residence conversion to ADU and 389 square foot garage conversion to\nJADU","Historic Preservat ion",null,"Pendi ng",{"$nulls":5},"Comment Letter sent 5-24-\n22",null,"5/24/2\n022","Bao Pham","bao@bdpeng.com"]
["Walnut","822 E\nWalnut\nAve","9286\n6","Huddlest on\nAddition","91 square foot addition to an existing bedroom. Add on new bathroom and a walk-in\ncloset.","Ani Mnatsak\nanyan",null,null,null,"Approved",null,null,null,"DRC Date: 11/16/22","7/5/20\n22","7/5/20\n22","John Marvick","JCMarvick@sbcglobal.n et","(714)\n476-\n3829"]
["Walnut","1212 E\nWalnut\nAve","9286\n7","Kroh/Sta ph ADU","New detached 748 SF ADU (2\nbedrooms 2 bathrooms) at rear of\nproperty","Ryan Agbayani",null,"Pendi ng",{"$nulls":5},"2/23/23 -\nIncomplet e Letter emailed to\napplicant.","1/3/20\n23",null,"Michael Kroh","krohmedia@gmail.com","(949)\n533-\n9575"]
["Walnut","4100 E\nWalnut Ave","9286\n9","Mike Davis","Request to increase student enrollment from 360 to\n540 students,\n4 portable classrooms, parking lot expansion, and related site","Monique Schwartz","Appr oved",null,null,null,"Approve d",null,"6/20/2\n022","Approved by PC on 6/20/202\n2",null,"1/18/2\n023","Michael Davis"]
[{"$nulls":4},"improvements\n."]
["Walnut","1103 W\nWalnut Ave","9286\n6","Nevarez ADU","New 450 SF\nADU attached to the existing detached garage.","Monique Schwartz",null,"Pendi ng",{"$nulls":5},"Incomplet e Letter sent 2/6/2023","1/3/20\n23","2/10/2\n023","John Carnes","isamu@pacificnet.net","(818)\n515-\n5702"]
["Washin gton","828 E\nWashin\ngton St","9286\n6","Carpente r ADU","A proposal to remodedl and add 424 square feet onto an existing ADU for a total of 652 square\nfeet","Ani Mnatsak\nanyan",null,"Pendi ng",{"$nulls":6},"11/30/\n2022","11/30/\n2022","Candace Carpenter","ansomedesigns@gmail. com","(562)\n595-\n3767"]
["Washin gton","4531 E\nWashin gton Ave","9286\n9","First Golden Village Orange Hill, LLC","A request to construct a new duplex on a vacant lot.","Monique Schwartz","Pendi ng",null,"Pendi ng","Pending",{"$nulls":5},"11/15/\n2022","Catie Vuong",null,"(714)\n260-\n4994"]
["Waverl y","156 N\nWaverl y St","9286\n6","Arkin ADU","New 387 SF\nADU attached to the rear of a detached\ngarage","Ani Mnatsak anyan",null,"Pendi ng",{"$nulls":6},"2/21/2\n023",null,"Blue Home Solutions","contact@bluehome.sol utions","(949)\n570-\n8300"]
["Waverl y","163 N\nWaverl y St","9286\n6","McLean Residenc e","Demolition of a portion of a non- contributing 218 square foot addition to the rear of a historic Pueblo home and the addition of a\nproposed 356 square feet to","Ani Mnatsak anyan",null,null,null,"Approved",null,null,null,"Approved by DRC on 11/2/202\n2","5/20/2\n022","5/23/2\n022","Ryan & Brittany McLean","rmclean33@gmail.com"]
[{"$nulls":4},"the house that includes a living room and a master suite."]
["Waverl y","562 N\nWaverl y St","9286\n7","Waverly ADU","A request to construct a new 800 square foot\nADU.","Tiffany Chhan/M onique Schwartz",null,"Pendi ng",{"$nulls":5},"Incomplet e letter sent on 2/10/202\n3","8/10/2\n022","2/10/2\n023","Mark W Murphy","mark@stack-llc.com","(310)\n803-\n6510"]
["Waverl y","272 S\nWaverl y St","9286\n6","Huber ADU","New detached 506 SF ADU.","Ani Mnatsak\nanyan",null,"Appro ved",{"$nulls":4},"2/28/2\n023",null,null,null,"Phillip Bennett","bpbarchitect@aol.com","(714)\n997-\n4956"]
["Wildern ess","7112 E\nWildern ess Ave","9286\n6","Mills ADU","Proposed construction of a ADU, 2\nbed and 2 bath","Tiffany Chhan",null,"Pendi ng",{"$nulls":5},"Incomplet e letter sent\n6/3/21","5/10/2\n021","10/4/2\n022","Mark Mills","mmills899@att.net","(949)\n795-\n2808"]
["Willow","1932 W\nWillow Ave","9286\n8","Genchev ADU","New detached 744 SF ADU","Ryan Agbayani",null,"Pendi ng",{"$nulls":6},"1/23/2\n023",null,"Jose Luigi Salemi","salemijr@yahoo.com","(949)\n302-\n7336"]
["Willow","1932 W\nWillow Ave","9286\n8","Genchev ADR","New 2nd story addition to an existing 1 story\nresidence.","Ryan Agbayani",null,"Pendi ng",{"$nulls":6},"1/23/2\n023",null,"Jose Luigi Salemi","salemijr@yahoo.com","(949)\n302-\n7336"]
["Wilson","333 E\nWilson\nAve","9286\n7","Lozano ADU","Convert an existing attached garage into a\n391 SF ADU","Ryan Agbayani",null,"Appro ved",{"$nulls":5},"3/15/202\n3","12/22/\n2022","3/15/2\n023","Ryan Lazano","ryanolazano@gmail.co m","(714)\n470-\n2080"]
["Wilson","2727 E\nWilson\nAve","9286\n7","Wilson ADU","Convert an existing detached garage 440 SF into a one bedroom one bathroom\nADU; new 264","Ryan Agbayani",null,"Pendi ng",{"$nulls":5},"2/22/23 -\nIncomplet e letter sent to applicant\nvia email.","12/15/\n2022",null,"Lam Nguyen","cumulusdesignbuild@g mail.com","(714)\n657-\n9333"]
[{"$nulls":4},"addition to ADU for a \"workshop\""]
["Windes","1955\nWindes Dr","9286\n9","Deacon Residenc e","A request to construct a new single story residence and barn on the site of a residence lost\nto wildfire.","Monique Schwartz","Appr oved","Appro ved",{"$nulls":4},"6/1/20\n20",null,null,"9/28/2\n022","Jon Christner",null,"(949)\n487-\n1863"]
["Woodsi de","1844 N\nWoodsi de St","9286\n5","Ahern Wooden Fence","Proposed 7 foot high wooden fence at rear of property between\nneighbors.","Ani Mnatsak anyan",null,null,"Appr oved",{"$nulls":4},"Permit issued","9/7/20\n22","9/12/2\n022","Bonny Ahern","bonnyahern@gmail.co m","(562)\n537-\n7649"]
["Yorba","190 S\nYorba St","9286\n9","Yorba Park Wireless Facility","Proposed 65 foot tall stealth tower with 15 antennas, an equipment enclosure, and various associated support equipment in\nYorba Park.","Vidal F. Márquez","Appr oved",null,null,null,"Pending",null,null,"Under review with Communi ty Services","8/11/2\n022","2/6/20\n23","Jermaine Taylor","jttelecoms@gmail.com","(909)\n917-\n1727"]